## Introduction
This workbook presents Gantt charts showing the projected U.S. Offshore wind project pipeline through 2035 for a number of development scenarios. The worksheets are described below.
Worksheet name | worksheet description
Assumptions | All assumptions used in this analysis are presented here.
Aggregated | This sheet represents the aggregated information from all projects, undeveloped lease areas, and Wind Energy Areas that are included in this study.
EC-UNC | Gantt chart for the unconstrained project pipeline scenario for the EAST COAST. This scenario assumes there are no constraints on supply of any components nor of vessels to complete projects installations. CODs are either those published by the developer or estimated based on available project information.
EC-LOW | Gantt chart for the "low" constrained project pipeline scenario for the EAST COAST. This scenario assumes there are relatively low constraints on turbine supply and vessels needed to complete project installations.
EC-MED | Gantt chart for the "medium" constrained project pipeline scenario for the EAST COAST. This scenario assumes there are relatively low constraints on turbine supply and vessels needed to complete project installations.
EC-HIGH | Gantt chart for the "high" constrained project pipeline scenario for the EAST COAST. This scenario assumes there are relatively low constraints on turbine supply and vessels needed to complete project installations.
GBF-UNC | Gantt chart for the EAST COAST scenario where it is assumed there is equal demand for all three fixed-bottom turbine foundation types (monopile, jacket, and GBF). This scenario assumes there are no constraints on obtaining each foundation type.
WC-UNC | Gantt chart for the unconstrained project pipeline scenario for the WEST COAST. This scenario assumes there are no constraints on supply of any components nor of vessels to complete projects installations. CODs are either those published by the developer or estimated based on available project information.
TOTAL-UNC | Gantt chart for the unconstrained project TOTAL pipeline scenario, EAST and WEST COAST. This scenario assumes there are no constraints on supply of any components nor of vessels to complete projects installations. CODs are either those published by the developer or estimated based on available project information.
ACCEL | Gantt chart for the ACCELERATED project TOTAL pipeline scenario, EAST and WEST COAST. This scenario assumes that once the pipeline reaches it's maximum capacity, the buildout continues at that pace through 2035.

## Assumptions
DESCRIPTION:
This sheet contains ALL project assumptions used in the following worksheets to develop the (GREEN) output sheets, one sheet per scenario
Parameters in the RED boxes can be changed and updates will show up in the GREEN output sheets.
KEY:
| Assumptions |  |  |  |  | input
1 | Scenarios |  |  |  |  | calculated
Unconstrained scenario:
| Assumes projects are developed according to Developers' timelines with no constraints on WTG supply and WTIVs. | [10 empty] | Tier 1: finished components
[7 empty] | 8 | Foundations |  |  |  | WTG 12 MW
| Constrained scenarios: | LOW | MED | HIGH | Manuf ramp-up, | % Available for US |  | Type | min depth, m | max depth, m | Notes | WTG 15 MW
| Total MW available for export from Europe, annually | 4000 | 3000 | 2000 | 33% |  |  | Monopile | 0 | 40 | Preferred option (least cost, most used in Europe, simplest, quickest to install). Monopile factory in NJ being constructed by EEW (Orsted). | WTG 18 MW
| Total # of WTIVs available | 9 | 7 | 5 |  | 50% |  | Gravity Base Foundation (GBF) | 20 | 40 | Can be manufactured in US, but more expensive than monopile and jacket (see GBS Foundation sheet). Half of Equinor projects, and half of shallower parts of NY Bight | Monopile
[8 empty] | Jacket | 40 | 60 | Can be manufactured in US | Transition piece
2 | Turbine size (Applied to Undeveloped areas): | [10 empty] | Gravity base
| Turbine Size | sm | med | lg | AVG |  |  | Foundation sensitivity study | % of Total |  |  | Jacket
| COD <= 2026 | 11 | 12 | 13 | 12 |  |  | Monopile | 33.33% |  |  | OSS Jacket
| 2026 < COD <= 2030 | 14 | 15 | 16 | 15 |  |  | Gravity base foundation (GBF) | 33.33% |  |  | Offshore substation
| 2030 < COD <= 2035 | 17 | 18 | 19 | 18 |  |  | Jacket | 33.33% |  |  | Array cables
| Standard development % of Lease Area | 65% | [9 empty] | Export cables
| Build-out lag time for remaining Lease Area | 2 | years
Tier 2: subassemblies
3 | Substations | [5 empty] | 9 | Vessels |  |  |  | Rotor blades: 107m, 115m, 125m
| MW/Substation | 800 | MW |  |  |  |  | Vessel Parameters | Value | Units | Notes | Nacelle: 12MW, 15 MW, 18MW
[8 empty] | Feeder barge min size | 90 | m |  | Tower: 110m, 120m, 130m
4 | Array and Export Cables | [6 empty] | WTIV per turbine | 36 | hr | 48 h too high, might be as low as 24 h
| Array cable margin | 10% | [5 empty] | WTIV per foundation | 36 | hr | 48 h too high
| Distance between turbines, nm | 1 | [5 empty] | HLV, per substation | 240 | hr |  | States
[8 empty] | Rock damping, per MP | 36 | hr | incl. re-loading
[8 empty] | Feeder barge transit time | 12 | hr |  | States | Abbrev. | No.
5 | Weather Window | [6 empty] | Feeder barge time on site | 108 | hr |  | Maine | ME | 1
| Quarter | % active time | Notes |  |  |  |  | WTG's per barge | 3 | # |  | New Hampshire | NH | 2
| Q1 | 33.1% | "Red Period" Jan-April no pile-driving due to Right Whale activity |  |  |  |  | Barge mob time | 36 | hr |  | Massachusetts | MA | 3
| Q2 | 66.67% | "Red Period" ends April 30, "Yellow period" May 1-15 | [8 empty] | Rhode Island | RI | 4
| Q3 | 100% | [5 empty] | CTVs | # required | Units | Notes | Connecticut | CT | 5
| Q4 | 66.67% | "Yellow Period" Nov |  |  |  |  | Construction year 0 | 2 | # |  | New York | NY | 6
| Annual factor: | 66.61% | % of year when construction is possible. |  |  |  |  | Year 1 | 2 | # |  | New Jersey | NJ | 7
| Assume Project is installed within one year (during Q2/Q3 weather window) | [6 empty] | Year 2 - 20 | 1 | # |  | Delaware | DE | 8
| Tufts study -- restrictions + weather windows justify 8 month (2/3) ocnstruction window | [6 empty] | initial CTV need | 2 | # | Existing projects (Block island, CVOW demo) | Maryland | MD | 9
[12 empty] | Virginia | VA | 10
6 | Turbine spacing | [6 empty] | Cable-laying vessels | Value | Units | Notes | North Carolina | NC | 11
| One turbine per nm2 | 1 | nm2 |  |  |  |  | Cable Laying speed | 4 | km/day |  | South Carolina | SC | 12
[8 empty] | Mob/demob time | 20 | days |  | California | CA | 13
7 | Procurement, Transport, Construction, Installation Timelines
| Procurement & manufacturing | Duration | Units
| Blades | 1 | yr
| Nacelle | 1 | yr |  |  |  | 10 | Toggle to INCLUDE/EXCLUDE (change these on Annual Gantt Chart sheet)
| Tower | 1 | yr |  |  |  |  | Include Projects | 1
| OSS | 2 | yr |  |  |  |  | Include Undeveloped areas | 1
| Array cables | 1 | yr
| Export cables | 1 | yr
| Monopile | 1 | yr
| GBS foundation | 1 | yr |  |  |  | 11 | Conversions:
| Jacket foundation | 1 | yr |  |  |  |  | Acres per NM^2 | 847.548
| OSS Jacket | 1 | yr |  |  |  |  | km per mile | 1.6093
| Transport & storage | 1 | yr |  |  |  |  | nautical miles per mile | 0.86897
| Start of construction to COD | 1 | yr |  |  |  |  | km per NM | 1.852
[8 empty] | acres per km^2 | 247.1054
[8 empty] | km^2/nm^2 | 3.4299
Other Assumptions:
1 | NY Bight lease areas included in analysis
2 | Additional Call Areas and WEAs along the East Coast (e.g., Wilmington East, NC and Grand Strand, SC) not included, due to uncertainty regarding project development
3 | CA WEAs (Morro Bay and Humboldt) is currently not included, but will be
4 | GoM is not included in the analysis
5 | % developable remaining lease areas for existing projects was reduced after discussion with Emily Lindow of BOEM: she anticipates opposition to developing remaining lease areas
6 | Assumed turbine spacing of 1 WTG per nm2 yields turbine density ranging from 3.5MW/km^2 for 12 MW turbines, which is slightly higher than the NREL 2020 Offhsore Wind Technologies Market Report, up to 5.3MW/km^2 for 18 MW turbines.
7 | Spacing of 1 nm between turbines is approximately 8.3 rotor diameters for the largest known rotors (222 m diameter).
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: After meeting w/Emily Lindow, Chief of Staff @BOEM, reducing this to 60%, and further reducing the "remaining lease areas" acreage to 30%. She explained that recent conversations with fisheries indicated they would likely oppose projects further building out their lease areas, at least initially. So we can't count on more than an additional 5 GW from those leftover lease areas.

## Aggregated
[22 empty] | Transposed Table | Project COD
Project COD | Total Lease Area, Acres | Number of Projects | Total Project Capacity, MW | Total # of 12 MW turbines | Total # of 15 MW turbines | Total # of 18 MW turbines | Average Rated Power, MW | AverageMin Water Depth, m | Average Max Water Depth, m | substructure: total monopiles, # | substructure: total GBF, # | substructure: total jacket, # | substructure: Total OSP jacket, # | # of OSP | array cable length per turbine, km | Total cable array length, km | export cable length, km | # of export cables | Total export cable length, km | HVAC | HVDC | DEFINED PROJECTS | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | EC-UNDEVELOPED | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | WC-UNDEVELOPED | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
PROJECTS | [21 empty] | Total Lease Area, Acres | 0 | 55200 | 508588.6667 | 310477.6667 | 186336.6667 | 224046.5 | 314249 | 0 | 159694 | 0 | 93761.5 | 0 | 0 | 0 | Total Lease Area, Acres | [14 empty] | Total Lease Area, Acres
2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Number of Projects | 0 | 2 | 6 | 5 | 5 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | Number of Projects | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 3 | 4 | 1 | 2 | 1 | 2 | 1 | Number of Projects | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0
2023 | 55200 | 2 | 532 | 42.7692 | 0 | 0 | 12 | 36 | 44.5 | 32.7692 | 0 | 10 | 2 | 2 | 2.6876 | 125.5024 | 256 | 2 | 256 | 2 | 0 | Total Project Capacity, MW | 0 | 532 | 4304 | 3802 | 2821 | 2368.6 | 2737 | 0 | 1797 | 0 | 759 | 0 | 0 | 0 | Total Project Capacity, MW | 0 | 0 | 0 | 0 | 608 | 536 | 2888.9938 | 2294 | 2931.9377 | 699.9506 | 2652.2678 | 1067 | 1441.4916 | 924 | Total Project Capacity, MW | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 1000 | 500 | 0 | 0 | 0 | 0
2024 | 508588.6667 | 6 | 4304 | 261.7949 | 76.521 | 0 | 12.9333 | 24.1667 | 37.3333 | 229.4935 | 29.1429 | 79.6795 | 10 | 10 | 2.5085 | 862.2539 | 552.6603 | 10 | 926.4136 | 10 | 0 | Total # of 12 MW turbines | 0 | 42.7692 | 261.7949 | 187.5128 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total # of 12 MW turbines | 0 | 0 | 0 | 0 | 50.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total # of 12 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 310477.6667 | 5 | 3802 | 187.5128 | 102.3333 | 0 | 13.2 | 34.82 | 47.3 | 179.5064 | 12 | 76.3397 | 9 | 6 | 2.4521 | 725.5871 | 462.5 | 6 | 505.5 | 6 | 0 | Total # of 15 MW turbines | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 157.9067 | 182.4667 | 0 | 119.8 | 0 | 0 | 0 | 0 | 0 | Total # of 15 MW turbines | 0 | 0 | 0 | 0 | 0 | 35.7333 | 192.5996 | 152.9333 | 195.4625 | 0 | 0 | 0 | 0 | 0 | Total # of 15 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0
2026 | 186336.6667 | 5 | 2821 | 10 | 183.0667 | 0 | 14.2 | 26.6 | 35.2 | 110.0667 | 11 | 50 | 6 | 6 | 2.1146 | 409.009 | 297.679 | 6 | 340.679 | 6 | 0 | Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.1667 | 0 | 0 | 0 | Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 147.3482 | 59.2778 | 80.0829 | 51.3333 | Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0
2027 | 224046.5 | 2 | 2368.6 | 0 | 157.9067 | 0 | 15 | 32.5 | 45 | 72.2 | 0 | 85.7067 | 4 | 4 | 2.1362 | 339.1801 | 173 | 4 | 393 | 4 | 0 | Average Rated Power, MW | 0 | 12 | 12.9333 | 13.2 | 14.2 | 15 | 15 | 0 | 15 | 0 | 18 | 0 | 0 | 0 | Average Rated Power, MW | 0 | 0 | 0 | 0 | 12 | 15 | 15 | 15 | 15 | 18 | 18 | 18 | 18 | 18 | Average Rated Power, MW | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 18 | 0 | 0 | 0 | 0
2028 | 314249 | 3 | 2737 | 0 | 182.4667 | 0 | 15 | 39.3333 | 50 | 65.0467 | 41 | 76.42 | 4 | 4 | 3.3956 | 582.028 | 235.405 | 4 | 335.405 | 4 | 0 | AverageMin Water Depth, m | 0 | 36 | 24.1667 | 34.82 | 26.6 | 32.5 | 39.3333 | 0 | 29.55 | 0 | 38 | 0 | 0 | 0 | AverageMin Water Depth, m | 0 | 0 | 0 | 0 | 27.4 | 50 | 26.9808 | 29.6154 | 34.5 | 30 | 25.5 | 38 | 38 | 31 | AverageMin Water Depth, m | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 722 | 722 | 900 | 0 | 0 | 0 | 0
2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Average Max Water Depth, m | 0 | 44.5 | 37.3333 | 47.3 | 35.2 | 45 | 50 | 0 | 42.75 | 0 | 60 | 0 | 0 | 0 | Average Max Water Depth, m | 0 | 0 | 0 | 0 | 0 | 60 | 39.9808 | 38.9487 | 48.75 | 30 | 38.5 | 50 | 52.5 | 43 | Average Max Water Depth, m | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1050 | 1050 | 1200 | 0 | 0 | 0 | 0
2030 | 159694 | 2 | 1797 | 0 | 119.8 | 0 | 15 | 29.55 | 42.75 | 107.35 | 0 | 12.45 | 6 | 3 | 4.4743 | 525 | 154.5 | 3 | 197.5 | 2 | 1 | substructure: total monopiles, # | 0 | 32.7692 | 229.4935 | 179.5064 | 110.0667 | 72.2 | 65.0467 | 0 | 107.35 | 0 | 12.65 | 0 | 0 | 0 | substructure: total monopiles, # | 0 | 0 | 0 | 0 | 50.6667 | 17.8667 | 148.9449 | 136.6 | 141.7292 | 38.8861 | 73.6741 | 19.7593 | 41.5273 | 25.6667 | substructure: total spar buoys, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | substructure: total GBF, # | 0 | 0 | 29.1429 | 12 | 11 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | substructure: total GBF, # | 0 | 0 | 0 | 0 | 0 | 0 | 11.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 | substructure: total semi-subs, # | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0
2032 | 93761.5 | 1 | 759 | 0 | 0 | 42.1667 | 18 | 38 | 60 | 12.65 | 0 | 29.5167 | 1 | 1 | 7.0974 | 299.274 | 72.405 | 1 | 72.405 | 1 | 0 | substructure: total jacket, # | 0 | 10 | 79.6795 | 76.3397 | 50 | 85.7067 | 76.42 | 0 | 12.45 | 0 | 29.5167 | 0 | 0 | 0 | substructure: total jacket, # | 0 | 0 | 0 | 0 | 0 | 17.8667 | 11.6222 | 0 | 32.4 | 0 | 0 | 19.7593 | 19.2778 | 0 | substructure: total TLP, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | substructure: Total OSP jacket, # | 0 | 2 | 10 | 9 | 6 | 4 | 4 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | substructure: Total OSP jacket, # | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 5 | 1 | 5 | 2 | 3 | 2 | substructure: Total OSPsemi-sub, # | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0
2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | # of OSP | 0 | 2 | 10 | 6 | 6 | 4 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | # of OSP | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 5 | 1 | 5 | 2 | 3 | 2 | # of OSP, floating | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0
2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Static array cable length per turbine, km | 0 | 2.6876 | 2.5085 | 2.4521 | 2.1146 | 2.1362 | 3.3956 | 0 | 4.4743 | 0 | 7.0974 | 0 | 0 | 0 | Static array cable length per turbine, km | 0 | 0 | 0 | 0 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | Dynamic array cable length per turbine, km | 0 | 0 | 0 | 0 | 0 | 0 | 3.66 | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 | 0
EC -UNDEVELOPED | [21 empty] | Total static array cable length, km | 0 | 125.5024 | 862.2539 | 725.5871 | 409.009 | 339.1801 | 582.028 | 0 | 525 | 0 | 299.274 | 0 | 0 | 0 | Total static array cable length, km | 0 | 0 | 0 | 0 | 111.264 | 78.4704 | 422.9487 | 335.8416 | 429.2357 | 85.394 | 323.5767 | 130.174 | 175.862 | 112.728 | Total dynamic array cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 244 | 244 | 101.6667 | 0 | 0 | 0 | 0
2022 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Static export cable length, km | 0 | 256 | 552.6603 | 462.5 | 297.679 | 173 | 235.405 | 0 | 154.5 | 0 | 72.405 | 0 | 0 | 0 | Static export cable length, km | 0 | 0 | 0 | 0 | 158 | 133 | 323.2603 | 402.2603 | 352.405 | 63 | 290 | 150 | 222.405 | 140 | Dynamic export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 105 | 0 | 0 | 0 | 0
2023 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | # of static export cables | 0 | 2 | 10 | 6 | 6 | 4 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | # of static export cables | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 5 | 1 | 5 | 2 | 3 | 2 | # of dynamic export cables | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0
2024 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total static export cable length, km | 0 | 256 | 926.4136 | 505.5 | 340.679 | 393 | 335.405 | 0 | 197.5 | 0 | 72.405 | 0 | 0 | 0 | Total static export cable length, km | 0 | 0 | 0 | 0 | 158 | 133 | 323.2603 | 690.2603 | 482.405 | 63 | 730 | 300 | 372.405 | 280 | Total dynamic export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 105 | 0 | 0 | 0 | 0
2025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVAC | 0 | 2 | 10 | 6 | 6 | 4 | 4 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 |  | 1 | 608 | 50.6667 | 0 | 0 | 12 | 27.4 | 0 | 50.6667 | 0 | 0 | 1 | 1 | 2.196 | 111.264 | 158 | 1 | 158 | 0 | 1 | HVDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | HVDC | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 2 | 0 | 5 | 2 | 2 | 2 | HVDC | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0
2027 |  | 1 | 536 | 0 | 35.7333 | 0 | 15 | 50 | 60 | 17.8667 | 0 | 17.8667 | 1 | 1 | 2.196 | 78.4704 | 133 | 1 | 133 | 0 | 1
2028 |  | 4 | 2888.9938 | 0 | 192.5996 | 0 | 15 | 26.9808 | 39.9808 | 148.9449 | 11.6222 | 11.6222 | 4 | 4 | 2.196 | 422.9487 | 323.2603 | 4 | 323.2603 | 3 | 1
2029 |  | 3 | 2294 | 0 | 152.9333 | 0 | 15 | 29.6154 | 38.9487 | 136.6 | 34.1333 | 0 | 5 | 5 | 2.196 | 335.8416 | 402.2603 | 5 | 690.2603 | 0 | 5

## EC-UNCONSTR
Toggle
| OUTPUT - EAST COAST UNCONSTRAINED DEMAND PIPELINE scenario | [14 empty] | EC-Projects | 1
[16 empty] | EC-Undeveloped | 1 |  | 1. link procurement timelines in column A (one for each item)
2. copy/paste from cell C10 into new row
|  | Year | [16 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL |  | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 419.095
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 568.5446 | 177.8333 | 240.2486 | 154 |  |  | 1257.285
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 419.095
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 419.095
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  |  | 1504.4034
1 | Transition Piece | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  |  | 1504.4034
1 | Jackets (turbine) | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 |  |  | 277.2762
1 | GBF (turbine) | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  |  | 521.0385
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  |  | 71
SUBSTATIONS
2 | OSS Topsides | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 0 |  |  | 63
CABLES
1 | Array cable, km | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 |  |  | 6073.3296
1 | Export cable, km | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 |  |  | 6559.2332
| Total Turbines | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 0 | 2370.6617
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 419.095
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 568.5446 | 177.8333 | 240.2486 | 154 |  | 1257.285
NACELLES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 419.095
TOWERS, m
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 419.095
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  | 1504.4034
1 | Transition Piece | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667
1 | Jackets (turbine) | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 |  | 277.2762
1 | GBF (turbine) | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  | 521.0385
1 | Jacket (Substation) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  | 71
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 |  | 65
CABLES
1 | Array cable, km | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 |  | 6073.3296
1 | Export cable, km | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 |  | 6559.2332
| Total Turbines | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 2370.6617
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 20592.332 | 22886.332 | 27615.2697 | 28315.2204 | 31726.4882 | 32793.4882 | 34234.9798 | 35158.9798 | 35158.9798
| Installed MW |  | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 5625.9938 | 2294 | 4728.9377 | 699.9506 | 3411.2678 | 1067 | 1441.4916 | 924 | 35158.9798
| Projects Constructed |  | 0 | 2 | 6 | 5 | 6 | 3 | 7 | 3 | 6 | 1 | 3 | 1 | 2 | 1 | 46
| TURBINES (total) | 0 | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2370.6617
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 419.095
ROTOR BLADES
| 12 |  | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 | 4196.4693
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 568.5446 | 177.8333 | 240.2486 | 154 | 1257.285
NACELLES
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 419.095
TOWERS
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 419.095
| FOUNDATIONS |  | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 170.7333 | 293.9292 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2302.7181
| Monopiles (turbine) |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 | 1504.4034
| Transition Piece |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 | 1504.4034 | 0.65332
| GBF (turbine) |  | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 | 277.2762 | 0.12041
| Jacket (turbine) |  | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 | 521.0385 | 0.22627
| Jacket (OSS) |  | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 | 71
SUBSTATIONS
| OSS Topside |  | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 65
CABLES, KM
| Static Array Cable, km |  | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 | 6073.3296
| Static Export Cable, km |  | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 | 6559.2332
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Mob/demob time to be added
| WTIV (15 MW) |  | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 562.5994 | 229.4 | 472.8938 | 0 | 0 | 0 | 0 | 0 |  |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3292 | 284.2723 | 88.9167 | 120.1243 | 77 |  |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 463.7595 | 383.7692 | 316.1 | 290.46 | 453.0507 | 204.9 | 440.8938 | 58.3292 | 173.7612 | 59.2778 | 91.2076 | 38.5
| WTIV total days |  |  | 128.3077 | 971.2334 | 818.5385 | 681.7 | 580.92 | 1015.65 | 434.3 | 913.7875 | 116.6584 | 458.0335 | 148.1944 | 211.3319 | 115.5
| HLV (Substation) |  | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 50 | 80 | 10 | 60 | 20 | 30 | 20
| CLV |  | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 837.9105 | 432.5255 | 766.5352 | 93.0985 | 588.3139 | 181.5435 | 251.0667 | 166.182
| Rock dumping |  | 0 | 49.1538 | 344.2403 | 269.2596 | 241.1 | 135.1 | 320.9873 | 204.9 | 373.6188 | 58.3292 | 129.4862 | 29.6389 | 62.291 | 38.5
VESSELS
| WTIV (12 MW) |  | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 5 | 5 | 5 | 4 | 5 | 2 | 4 | 2 | 3 | 2 | 2 | 2
|  |  |  | 1 | 4 | 4 | 3 | 3 | 5 | 2 | 4 | 1 | 2 | 1 | 1 | 1
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Feeder Barges |  | 0 | 4 | 10 | 10 | 10 | 8 | 10 | 4 | 8 | 4 | 6 | 4 | 4 | 4
| CTV |  | 0 | 6 | 18 | 26 | 32 | 33 | 41 | 44 | 49 | 48 | 48 | 49 | 50 | 51 | 51
| CLV |  | 0 | 1 | 4 | 3 | 3 | 2 | 4 | 2 | 4 | 1 | 3 | 1 | 2 | 1
| scour protection vessel |  | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) |  | 0 | 3 | 8 | 8 | 8 | 6 | 8 | 3 | 6 | 3 | 5 | 3 | 3 | 3
| EC Lay-down Area (acres) |  | 0 | 29 | 116 | 116 | 87 | 87 | 145 | 58 | 116 | 29 | 58 | 29 | 29 | 29
| Total Turbines |  | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2370.6617

## EC-LOW
LOW - Low Constrained scenario
Year
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTALS
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
| TURBINES ORDERED, MW | 42.7692 | 154 | 254.6667 | 300 | 199.9744 | 266.6667 | 266.6667 | 266.6667 | 172.2195 | 177.9342 | 111.1111 | 106.6533 | 51.3333 | 0 | 0 | 2370.6617
1 | 12 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 |  |  | 419.095
ROTOR BLADES, m
1 | 12 | 128.3077 | 330 | 500 | 500 | 199.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 132 | 264 | 400 | 400 | 800 | 800 | 800 | 400 | 200.4693 | 0 | 0 | 0 |  |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 333.3333 | 333.3333 | 319.9599 | 154 |  |  | 1257.285
NACELLES, MW
1 | 12 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 |  |  | 419.095
TOWERS, m
1 | 12 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 |  |  | 419.095
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 172.2195 | 81.0491 | 37.037 | 55.3055 | 25.6667 |  |  | 1558.0994
1 | Transition Piece | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 172.2195 | 81.0491 | 37.037 | 55.3055 | 25.6667 |  |  | 1558.0994
1 | Jackets (turbine) | 0 | 13.2657 | 10.5435 | 13.5394 | 0 | 37.4136 | 59.5176 | 0 | 0 | 69.1721 | 37.037 | 25.6739 | 25.6667 |  |  | 291.8295
1 | GBF (turbine) | 10 | 36.2698 | 67.0742 | 61.5427 | 106.9614 | 62.5967 | 0 | 37.9366 | 0 | 27.713 | 37.037 | 25.6739 | 0 |  |  | 472.8053
1 | Jacket (Substation) | 2 | 4.552 | 7.9076 | 8.616 | 5.1636 | 5.6879 | 8.7184 | 9.3044 | 4.4288 | 5.6334 | 3.7488 | 3.9954 | 2 |  |  | 71.7562
SUBSTATIONS
2 | OSS Topsides | 4.6161 | 5.2627 | 8.0599 | 4.8194 | 5.6879 | 8.7184 | 6.7668 | 3.8573 | 5.2808 | 3.7488 | 3.9954 | 2 | 0 |  |  | 62.8134
CABLES
1 | Array cable, km | 125.5024 | 398.0233 | 636.4205 | 599.0478 | 402.5659 | 714.5238 | 585.6 | 807.1459 | 329.394 | 548.1873 | 244 | 234.2107 | 112.728 |  |  | 5737.3495
1 | Export cable, km | 256 | 427.6399 | 443.3796 | 574.1842 | 507.002 | 468.3015 | 1203.5925 | 575.1017 | 243.0127 | 706.2178 | 562.3243 | 495.964 | 280 |  |  | 6742.7203
0
TRANSPORT
| TURBINES, MW | 0 | 42.7692 | 154 | 254.6667 | 300 | 199.9744 | 266.6667 | 266.6667 | 266.6667 | 172.2195 | 177.9342 | 111.1111 | 106.6533 | 51.3333 | 0 | 2370.6617
1 | 12 | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 |  | 419.095
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 330 | 500 | 500 | 199.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 132 | 264 | 400 | 400 | 800 | 800 | 800 | 400 | 200.4693 | 0 | 0 | 0 |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 333.3333 | 333.3333 | 319.9599 | 154 |  | 1257.285
NACELLES, MW
1 | 12 | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 |  | 419.095
TOWERS, m
1 | 12 | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 |  | 419.095
| FOUNDATIONS |  | 42.7692 | 154 | 235.3369 | 272.9212 | 199.9744 | 252.1553 | 297.7042 | 248.6217 | 172.2195 | 177.9342 | 111.1111 | 106.6533 | 51.3333 | 0 | 2322.7343
1 | Monopiles (turbine) | 0 | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 172.2195 | 81.0491 | 37.037 | 55.3055 | 25.6667 |  | 1558.0994
1 | Transition Piece | 0 | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 172.2195 | 81.0491 | 37.037 | 55.3055 | 25.6667
1 | Jackets (turbine) | 0 | 0 | 13.2657 | 10.5435 | 13.5394 | 0 | 37.4136 | 59.5176 | 0 | 0 | 69.1721 | 37.037 | 25.6739 | 25.6667 |  | 291.8295
1 | GBF (turbine) | 0 | 10 | 36.2698 | 67.0742 | 61.5427 | 106.9614 | 62.5967 | 0 | 37.9366 | 0 | 27.713 | 37.037 | 25.6739 | 0 |  | 472.8053
1 | Jacket (Substation) | 0 | 2 | 4.552 | 7.9076 | 8.616 | 5.1636 | 5.6879 | 8.7184 | 9.3044 | 4.4288 | 5.6334 | 3.7488 | 3.9954 | 2 |  | 71.7562
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 4.6161 | 5.2627 | 8.0599 | 4.8194 | 5.6879 | 8.7184 | 6.7668 | 3.8573 | 5.2808 | 3.7488 | 3.9954 | 2 |  | 64.8134
CABLES
1 | Array cable, km | 0 | 125.5024 | 398.0233 | 636.4205 | 599.0478 | 402.5659 | 714.5238 | 585.6 | 807.1459 | 329.394 | 548.1873 | 244 | 234.2107 | 112.728 |  | 5737.3495
1 | Export cable, km | 0 | 256 | 427.6399 | 443.3796 | 574.1842 | 507.002 | 468.3015 | 1203.5925 | 575.1017 | 243.0127 | 706.2178 | 562.3243 | 495.964 | 280 |  | 6742.7203
VESSELS
0
0
NOTE: This table is the FOUNDATION, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 2493.2308 | 5813.2308 | 9813.2308 | 12612.9231 | 16612.9231 | 20612.9231 | 24612.9231 | 27312.8737 | 30315.2204 | 32315.2204 | 34234.9798 | 35158.9798 | 35158.9798
| Installed MW |  | 0 | 513.2308 | 1980 | 3320 | 4000 | 2799.6923 | 4000 | 4000 | 4000 | 2699.9506 | 3002.3467 | 2000 | 1919.7594 | 924 | 35158.9798
| Number of Projects |  | 0 | 2 | 3 | 5 | 5 | 4 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 50
| TURBINES |  | 0 | 42.7692 | 154 | 254.6667 | 300 | 199.9744 | 266.6667 | 266.6667 | 266.6667 | 172.2195 | 177.9342 | 111.1111 | 106.6533 | 51.3333 | 2370.6617
| 12 |  | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 | 419.095
ROTOR BLADES
| 12 |  | 0 | 128.3077 | 330 | 500 | 500 | 199.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 132 | 264 | 400 | 400 | 800 | 800 | 800 | 400 | 200.4693 | 0 | 0 | 0 | 4196.4693
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 333.3333 | 333.3333 | 319.9599 | 154 | 1257.285
NACELLES
| 12 |  | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 | 419.095
TOWERS
| 12 |  | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 111.1111 | 111.1111 | 106.6533 | 51.3333 | 419.095
FOUNDATIONS
| Monopiles (turbine) |  | 0 | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 172.2195 | 81.0491 | 37.037 | 55.3055 | 25.6667 | 1558.0994
| Transition Piece |  | 0 | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 172.2195 | 81.0491 | 37.037 | 55.3055 | 25.6667 | 1558.0994
| GBF (turbine) |  | 0 | 0 | 13.2657 | 10.5435 | 13.5394 | 0 | 37.4136 | 59.5176 | 0 | 0 | 69.1721 | 37.037 | 25.6739 | 25.6667 | 291.8295
| Jacket (turbine) |  | 0 | 10 | 36.2698 | 67.0742 | 61.5427 | 106.9614 | 62.5967 | 0 | 37.9366 | 0 | 27.713 | 37.037 | 25.6739 | 0 | 472.8053
| Jacket (Substation) |  | 0 | 2 | 4.552 | 7.9076 | 8.616 | 5.1636 | 5.6879 | 8.7184 | 9.3044 | 4.4288 | 5.6334 | 3.7488 | 3.9954 | 2 | 71.7562
SUBSTATIONS
| OSS Topside |  | 0 | 2 | 4.6161 | 5.2627 | 8.0599 | 4.8194 | 5.6879 | 8.7184 | 6.7668 | 3.8573 | 5.2808 | 3.7488 | 3.9954 | 2 | 64.8134
CABLES, KM
| Array cable, km |  |  | 125.5024 | 398.0233 | 636.4205 | 599.0478 | 402.5659 | 714.5238 | 585.6 | 807.1459 | 329.394 | 548.1873 | 244 | 234.2107 | 112.728 | 5737.3495
| Export cable, km |  |  | 256 | 427.6399 | 443.3796 | 574.1842 | 507.002 | 468.3015 | 1203.5925 | 575.1017 | 243.0127 | 706.2178 | 562.3243 | 495.964 | 280 | 6742.7203
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 64.1538 | 165 | 250 | 250 | 99.9615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 66 | 132 | 200 | 200 | 400 | 400 | 400 | 200 | 100.2347 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3292 | 166.6667 | 166.6667 | 159.98 | 77
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 211.1014 | 337.19 | 389.0728 | 299.9615 | 322.1125 | 357.2799 | 372.9326 | 258.3292 | 163.1432 | 111.1111 | 121.4691 | 38.5
| WTIV Total Days |  |  | 128.3077 | 442.1014 | 719.19 | 839.0728 | 599.9231 | 722.1125 | 757.2799 | 772.9326 | 516.6584 | 430.0445 | 277.7778 | 281.4491 | 115.5
| HLV (Substation) |  | 0 | 20 | 46.1608 | 52.6267 | 80.5987 | 48.1941 | 56.8788 | 87.184 | 67.6685 | 38.5734 | 52.8076 | 37.4883 | 39.9536 | 20
| CLV |  | 0 | 161.3756 | 366.4158 | 535.95 | 593.308 | 447.392 | 595.7063 | 747.2981 | 645.5619 | 359.1017 | 545.6013 | 361.5811 | 338.5437 | 186.182
| Rock damping |  | 0 | 49.1538 | 156.6968 | 236.5788 | 296.7588 | 139.5194 | 228.2173 | 357.2799 | 316.0277 | 258.3292 | 121.5737 | 55.5556 | 82.9583 | 38.5
VESSELS, (Vessels needed)
| WTIV (12 MW) |  | 0 | 1 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 3 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2
|  |  |  | 1 | 2 | 3 | 4 | 3 | 3 | 4 | 4 | 3 | 2 | 2 | 2 | 1
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| feeder Barges |  | 0 | 4 | 6 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 4
| CTV |  | 0 | 6 | 12 | 20 | 27 | 30 | 35 | 41 | 46 | 49 | 52 | 54 | 56 | 57 | 57
| CLV |  | 0 | 1 | 2 | 3 | 3 | 2 | 3 | 4 | 3 | 2 | 3 | 2 | 2 | 1 | 0
| Rock damping vessel |  |  | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1
Interim Calcs
# of turbines available to the US market
| 12 |  |  | 110 | 110 | 166.6667 | 166.6667 | 166.6667
| 15 |  |  |  | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 133.3333 | 133.3333 | 133.3333 | 133.3333 |  | IF(AND('OUTPUT-UNC'!E$86>0,'OUTPUT-UNC'!E$87=0,'OUTPUT-UNC'!E$88=0),(Assumptions!$C$9/$B134),IF(AND('OUTPUT-UNC'!E$86>0,'OUTPUT-UNC'!E$87>0,'OUTPUT-UNC'!E$88=0),(Assumptions!$C$9/$B134/2),IF(AND('OUTPUT-UNC'!E$86>0,'OUTPUT-UNC'!E$87=0,'OUTPUT-UNC'!E$88>0),Assumptions!$C$9/$B134/2,IF(AND('OUTPUT-UNC'!E$86>0,'OUTPUT-UNC'!E$87>0,'OUTPUT-UNC'!E$88>0),Assumptions!$C$9/$B134/3,0))))
| 18 | [10 empty] | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 111.1111
|  |  |  | 1320 | 1980 | 3320 | 4000 | 4000 | 4000 | 4000 | 4000 | 2880 | 4000 | 4000 | 4000 | 4000
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe here is the # of projects per year.

## EC-MED
MED - Medium Constrained scenario
Year
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTALS
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
| TURBINES ORDERED, MW | 42.7692 | 143 | 191 | 225 | 225 | 124.9744 | 100 | 66.6667 | 105.5528 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 0 | 0 | 1712.852
1 | 12 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 899
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 261.1084
ROTOR BLADES, m
1 | 12 | 128.3077 | 330 | 375 | 375 | 375 | 74.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 99 | 198 | 300 | 300 | 300 | 300 | 200 | 200 | 200 | 200 | 200 | 200 |  |  | 2697
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 166.6667 | 166.6667 | 166.6667 | 166.6667 |  |  | 783.3251
NACELLES, MW
1 | 12 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 899
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 261.1084
TOWERS, m
1 | 12 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 899
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 261.1084
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 89.32 | 52.6713 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  |  | 1040.844
1 | Transition Piece | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 89.32 | 52.6713 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  |  | 1040.844
1 | Jackets (turbine) | 0 | 12.3182 | 7.9076 | 10.1545 | 0 | 17.534 | 22.3191 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 |  |  | 249.021
1 | GBF (turbine) | 10 | 33.6791 | 50.3056 | 46.157 | 120.347 | 29.3362 | 0 | 9.4842 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 |  |  | 388.5075
1 | Jacket (Substation) | 2 | 4.2268 | 5.9307 | 6.462 | 5.8098 | 2.6656 | 3.2694 | 2.3261 | 2.7144 | 3.8695 | 4.1237 | 4.5786 | 4.7619 |  |  | 52.7386
SUBSTATIONS
2 | OSS Topsides | 4.2314 | 3.947 | 6.0449 | 5.1642 | 2.5591 | 3.2694 | 1.6917 | 2.4287 | 3.5178 | 3.7488 | 4.1624 | 4.329 | 0 |  |  | 45.0944
CABLES
1 | Array cable, km | 125.5024 | 364.8547 | 477.3153 | 449.2859 | 431.368 | 321.4808 | 219.6 | 201.7865 | 207.394 | 365.1725 | 244 | 244 | 244 |  |  | 3895.7601
1 | Export cable, km | 256 | 392.0033 | 332.5347 | 430.6382 | 543.2762 | 210.6996 | 451.3472 | 143.7754 | 153.0063 | 470.4439 | 562.3243 | 516.694 | 606.0606 |  |  | 5068.8036
0
TRANSPORT
| TURBINES, MW | 0 | 42.7692 | 143 | 191 | 225 | 225 | 124.9744 | 100 | 66.6667 | 105.5528 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 0 | 1712.852
1 | 12 | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 899
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 261.1084
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 330 | 375 | 375 | 375 | 74.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 99 | 198 | 300 | 300 | 300 | 300 | 200 | 200 | 200 | 200 | 200 | 200 |  | 2697
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 166.6667 | 166.6667 | 166.6667 | 166.6667 |  | 783.3251
NACELLES, MW
1 | 12 | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 899
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 261.1084
TOWERS, m
1 | 12 | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 899
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 261.1084
| FOUNDATIONS |  | 42.7692 | 143 | 176.5027 | 204.6909 | 225 | 118.1735 | 111.6391 | 62.1554 | 105.5528 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 0 | 1678.3725
1 | Monopiles (turbine) | 0 | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 89.32 | 52.6713 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  | 1040.844
1 | Transition Piece | 0 | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 89.32 | 52.6713 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111
1 | Jackets (turbine) | 0 | 0 | 12.3182 | 7.9076 | 10.1545 | 0 | 17.534 | 22.3191 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 |  | 249.021
1 | GBF (turbine) | 0 | 10 | 33.6791 | 50.3056 | 46.157 | 120.347 | 29.3362 | 0 | 9.4842 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 |  | 388.5075
1 | Jacket (Substation) | 0 | 2 | 4.2268 | 5.9307 | 6.462 | 5.8098 | 2.6656 | 3.2694 | 2.3261 | 2.7144 | 3.8695 | 4.1237 | 4.5786 | 4.7619 |  | 52.7386
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 4.2314 | 3.947 | 6.0449 | 5.1642 | 2.5591 | 3.2694 | 1.6917 | 2.4287 | 3.5178 | 3.7488 | 4.1624 | 4.329 |  | 47.0944
CABLES
1 | Array cable, km | 0 | 125.5024 | 364.8547 | 477.3153 | 449.2859 | 431.368 | 321.4808 | 219.6 | 201.7865 | 207.394 | 365.1725 | 244 | 244 | 244 |  | 3895.7601
1 | Export cable, km | 0 | 256 | 392.0033 | 332.5347 | 430.6382 | 543.2762 | 210.6996 | 451.3472 | 143.7754 | 153.0063 | 470.4439 | 562.3243 | 516.694 | 606.0606 |  | 5068.8036
VESSELS
0
0
NOTE: This table is the FOUNDATION, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 2328.2308 | 4818.2308 | 7818.2308 | 10818.2308 | 12617.9231 | 14117.9231 | 15117.9231 | 16817.8737 | 18817.8737 | 20817.8737 | 22817.8737 | 24817.8737 | 24817.8737
| Installed MW |  | 0 | 513.2308 | 1815 | 2490 | 3000 | 3000 | 1799.6923 | 1500 | 1000 | 1699.9506 | 2000 | 2000 | 2000 | 2000 | 24817.8737
| Number of Projects |  | 0 | 2 | 3 | 4 | 4 | 4 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 39
| TURBINES, MW | 0 | 0 | 42.7692 | 143 | 191 | 225 | 225 | 124.9744 | 100 | 66.6667 | 105.5528 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 1712.852
| 12 |  | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 899
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 261.1084
ROTOR BLADES, UNITS
| 12 |  | 0 | 128.3077 | 330 | 375 | 375 | 375 | 74.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 99 | 198 | 300 | 300 | 300 | 300 | 200 | 200 | 200 | 200 | 200 | 200 | 2697
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 166.6667 | 166.6667 | 166.6667 | 166.6667 | 783.3251
NACELLES, MW
| 12 |  | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 899
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 261.1084
TOWERS, UNITS
| 12 |  | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 899
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 261.1084
FOUNDATIONS
| Monopiles (turbine) |  | 0 | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 89.32 | 52.6713 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 | 1040.844
| Transition Piece |  | 0 | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 89.32 | 52.6713 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 | 1040.844
| GBF (turbine) |  | 0 | 0 | 12.3182 | 7.9076 | 10.1545 | 0 | 17.534 | 22.3191 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 | 249.021
| Jacket (turbine) |  | 0 | 10 | 33.6791 | 50.3056 | 46.157 | 120.347 | 29.3362 | 0 | 9.4842 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 | 388.5075
| Jacket (Substation) |  | 0 | 2 | 4.2268 | 5.9307 | 6.462 | 5.8098 | 2.6656 | 3.2694 | 2.3261 | 2.7144 | 3.8695 | 4.1237 | 4.5786 | 4.7619 | 52.7386
SUBSTATIONS
| OSS Topside |  | 0 | 2 | 4.2314 | 3.947 | 6.0449 | 5.1642 | 2.5591 | 3.2694 | 1.6917 | 2.4287 | 3.5178 | 3.7488 | 4.1624 | 4.329 | 47.0944
CABLES, KM
| Array cable, km |  |  | 125.5024 | 364.8547 | 477.3153 | 449.2859 | 431.368 | 321.4808 | 219.6 | 201.7865 | 207.394 | 365.1725 | 244 | 244 | 244 | 3895.7601
| Export cable, km |  |  | 256 | 392.0033 | 332.5347 | 430.6382 | 543.2762 | 210.6996 | 451.3472 | 143.7754 | 153.0063 | 470.4439 | 562.3243 | 516.694 | 606.0606 | 5068.8036
VESSELS, (Vessel.Day)
| WTIV (12 MW) |  | 0 | 64.1538 | 165 | 187.5 | 187.5 | 187.5 | 37.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 49.5 | 99 | 150 | 150 | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3292 | 83.3333 | 83.3333 | 83.3333 | 83.3333
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 196.0228 | 252.8925 | 291.8046 | 337.5 | 150.9592 | 133.9799 | 93.2332 | 158.3292 | 112.0623 | 122.2222 | 139.2008 | 91.6667
| WTIV Total Days |  |  | 128.3077 | 410.5228 | 539.3925 | 629.3046 | 675 | 338.4208 | 283.9799 | 193.2332 | 316.6584 | 295.3956 | 305.5556 | 322.5341 | 275
| HLV (Substation) |  | 0 | 20 | 42.3141 | 39.47 | 60.4491 | 51.6422 | 25.5911 | 32.694 | 16.9171 | 24.2867 | 35.1775 | 37.4883 | 41.6236 | 43.29
| CLV |  | 0 | 161.3756 | 341.2145 | 408.4625 | 449.981 | 473.661 | 283.0451 | 283.7368 | 176.3905 | 236.1001 | 368.9041 | 361.5811 | 350.1735 | 372.5152
| Rock damping |  | 0 | 49.1538 | 145.5041 | 177.4341 | 222.5691 | 156.9794 | 106.9549 | 133.9799 | 79.0069 | 158.3292 | 83.5084 | 61.1111 | 95.0683 | 91.6667
VESSELS, (Vessels needed)
| WTIV (12 MW) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 3 | 4 | 4 | 4 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3
|  |  |  | 1 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| feeder Barges |  | 0 | 4 | 6 | 8 | 8 | 8 | 6 | 4 | 4 | 6 | 6 | 6 | 6 | 6
| CTV |  | 0 | 6 | 12 | 18 | 23 | 27 | 29 | 29 | 30 | 34 | 38 | 41 | 44 | 47 | 47
| CLV |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 0
| Rock damping vessel |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Interim Calcs
# of turbines available to the US market
| 12 |  |  | 82.5 | 110 | 125 | 125 | 125 | 125 | 125 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333
| 15 |  |  |  | 33 | 66 | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667
| 18 | [9 empty] | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556
|  |  |  | 990 | 1815 | 2490 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe here is the # of projects per year.

## EC-HIGH
HIGH - Highly Constrained scenario
Year
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTALS
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
| TURBINES ORDERED, MW | 42.7692 | 121.6667 | 150 | 150 | 150 | 150 | 150 | 104.9744 | 105.5528 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 0 | 0 | 1613.852
1 | 12 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 261.1084
ROTOR BLADES, m
1 | 12 | 128.3077 | 165 | 250 | 250 | 250 | 250 | 250 | 114.9231 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  |  | 2400
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 166.6667 | 166.6667 | 166.6667 | 166.6667 |  |  | 783.3251
NACELLES, MW
1 | 12 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 261.1084
TOWERS, m
1 | 12 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 261.1084
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  |  | 1005.8406
1 | Transition Piece | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  |  | 1005.8406
1 | Jackets (turbine) | 0 | 10.4805 | 6.2102 | 6.7697 | 0 | 21.0452 | 33.4786 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 |  |  | 256.7717
1 | GBF (turbine) | 10 | 28.6547 | 39.507 | 30.7713 | 80.2314 | 35.2107 | 0 | 14.9339 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 |  |  | 328.5073
1 | Jacket (Substation) | 2 | 3.5962 | 4.6576 | 4.308 | 3.8732 | 3.1994 | 4.9041 | 3.6627 | 2.7144 | 3.8695 | 4.1237 | 4.5786 | 4.7619 |  |  | 50.2494
SUBSTATIONS
2 | OSS Topsides | 3.87 | 3.1703 | 4.0299 | 3.4428 | 2.8439 | 4.3592 | 2.4694 | 2.4287 | 3.5178 | 3.7488 | 4.1624 | 4.329 | 0 |  |  | 42.3722
CABLES
1 | Array cable, km | 125.5024 | 333.6963 | 383.3858 | 299.5239 | 287.5787 | 357.2619 | 292.8 | 294.5462 | 207.394 | 365.1725 | 244 | 244 | 244 |  |  | 3678.8617
1 | Export cable, km | 256 | 358.5264 | 267.0961 | 287.0921 | 362.1841 | 234.1507 | 601.7963 | 209.8679 | 153.0063 | 470.4439 | 562.3243 | 516.694 | 606.0606 |  |  | 4885.2427
0
TRANSPORT
| TURBINES, MW | 0 | 42.7692 | 121.6667 | 150 | 150 | 150 | 150 | 150 | 104.9744 | 105.5528 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 0 | 1613.852
1 | 12 | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 261.1084
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 165 | 250 | 250 | 250 | 250 | 250 | 114.9231 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 2400
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 166.6667 | 166.6667 | 166.6667 | 166.6667 |  | 783.3251
NACELLES, MW
1 | 12 | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 261.1084
TOWERS, m
1 | 12 | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 261.1084
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  | 1005.8406
1 | Transition Piece | 0 | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111
1 | Jackets (turbine) | 0 | 0 | 10.4805 | 6.2102 | 6.7697 | 0 | 21.0452 | 33.4786 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 |  | 256.7717
1 | GBF (turbine) | 0 | 10 | 28.6547 | 39.507 | 30.7713 | 80.2314 | 35.2107 | 0 | 14.9339 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 |  | 328.5073
1 | Jacket (Substation) | 0 | 2 | 3.5962 | 4.6576 | 4.308 | 3.8732 | 3.1994 | 4.9041 | 3.6627 | 2.7144 | 3.8695 | 4.1237 | 4.5786 | 4.7619 |  | 50.2494
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 3.87 | 3.1703 | 4.0299 | 3.4428 | 2.8439 | 4.3592 | 2.4694 | 2.4287 | 3.5178 | 3.7488 | 4.1624 | 4.329 |  | 44.3722
CABLES
1 | Array cable, km | 0 | 125.5024 | 333.6963 | 383.3858 | 299.5239 | 287.5787 | 357.2619 | 292.8 | 294.5462 | 207.394 | 365.1725 | 244 | 244 | 244 |  | 3678.8617
1 | Export cable, km | 0 | 256 | 358.5264 | 267.0961 | 287.0921 | 362.1841 | 234.1507 | 601.7963 | 209.8679 | 153.0063 | 470.4439 | 562.3243 | 516.694 | 606.0606 |  | 4885.2427
VESSELS
0
0
NOTE: This table is the FOUNDATION, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 2173.2308 | 4173.2308 | 6173.2308 | 8173.2308 | 10173.2308 | 12173.2308 | 13632.9231 | 15332.8737 | 17332.8737 | 19332.8737 | 21332.8737 | 23332.8737 | 23332.8737
| Installed MW |  | 0 | 513.2308 | 1660 | 2000 | 2000 | 2000 | 2000 | 2000 | 1459.6923 | 1699.9506 | 2000 | 2000 | 2000 | 2000 | 23332.8737
| Number of Projects |  | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 37
| TURBINES, MW | 0 | 0 | 42.7692 | 121.6667 | 150 | 150 | 150 | 150 | 150 | 104.9744 | 105.5528 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 1613.852
| 12 |  | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 800
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 261.1084
ROTOR BLADES, UNITS
| 12 |  | 0 | 128.3077 | 165 | 250 | 250 | 250 | 250 | 250 | 114.9231 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 2400
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 166.6667 | 166.6667 | 166.6667 | 166.6667 | 783.3251
NACELLES, MW
| 12 |  | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 800
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 261.1084
TOWERS, UNITS
| 12 |  | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 800
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 261.1084
| FOUNDATIONS |  | 0 | 42.7692 | 121.6667 | 138.6146 | 136.4606 | 150 | 141.8373 | 167.4586 | 97.8709 | 105.5528 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 1591.1197
| Monopiles (turbine) |  | 0 | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 | 1005.8406
| Transition Piece |  | 0 | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 105.5528 | 55.6723 | 40.7407 | 63.3789 | 61.1111 | 1005.8406
| GBF (turbine) |  | 0 | 0 | 10.4805 | 6.2102 | 6.7697 | 0 | 21.0452 | 33.4786 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 | 256.7717
| Jacket (turbine) |  | 0 | 10 | 28.6547 | 39.507 | 30.7713 | 80.2314 | 35.2107 | 0 | 14.9339 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 | 328.5073
| Jacket (Substation) |  | 0 | 2 | 3.5962 | 4.6576 | 4.308 | 3.8732 | 3.1994 | 4.9041 | 3.6627 | 2.7144 | 3.8695 | 4.1237 | 4.5786 | 4.7619 | 50.2494
SUBSTATIONS
| OSS Topside |  | 0 | 2 | 3.87 | 3.1703 | 4.0299 | 3.4428 | 2.8439 | 4.3592 | 2.4694 | 2.4287 | 3.5178 | 3.7488 | 4.1624 | 4.329 | 44.3722
CABLES, KM
| Array cable, km |  |  | 125.5024 | 333.6963 | 383.3858 | 299.5239 | 287.5787 | 357.2619 | 292.8 | 294.5462 | 207.394 | 365.1725 | 244 | 244 | 244 | 3678.8617
| Export cable, km |  |  | 256 | 358.5264 | 267.0961 | 287.0921 | 362.1841 | 234.1507 | 601.7963 | 209.8679 | 153.0063 | 470.4439 | 562.3243 | 516.694 | 606.0606 | 4885.2427
VESSELS, (Vessel.Day)
| WTIV (12 MW) |  | 0 | 64.1538 | 82.5 | 125 | 125 | 125 | 125 | 125 | 57.4615 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3292 | 83.3333 | 83.3333 | 83.3333 | 83.3333
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 166.7793 | 198.6067 | 194.5364 | 225 | 181.1883 | 200.9699 | 146.8064 | 158.3292 | 112.0623 | 122.2222 | 139.2008 | 91.6667
| WTIV Total Days |  |  | 128.3077 | 349.2793 | 423.6067 | 419.5364 | 450 | 406.1883 | 425.9699 | 304.2679 | 316.6584 | 295.3956 | 305.5556 | 322.5341 | 275
| HLV (Substation) |  | 0 | 20 | 38.7005 | 31.7028 | 40.2994 | 34.4281 | 28.4394 | 43.592 | 24.6938 | 24.2867 | 35.1775 | 37.4883 | 41.6236 | 43.29
| CLV |  | 0 | 161.3756 | 317.0557 | 322.6205 | 306.654 | 322.4407 | 307.8532 | 383.6491 | 240.1035 | 236.1001 | 368.9041 | 361.5811 | 350.1735 | 372.5152
| Rock damping |  | 0 | 49.1538 | 123.7972 | 139.3461 | 148.3794 | 104.653 | 128.3723 | 200.9699 | 124.4055 | 158.3292 | 83.5084 | 61.1111 | 95.0683 | 91.6667
VESSELS, (Vessels needed)
| WTIV (12 MW) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| feeder Barges |  | 0 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| CTV |  | 0 | 6 | 12 | 16 | 19 | 22 | 25 | 28 | 29 | 32 | 36 | 39 | 42 | 45 | 45
| CLV |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 0
| Rock damping vessel |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Interim Calcs
# of turbines available to the US market
| 12 |  |  | 55 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333
| 15 |  |  |  | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667
| 18 | [10 empty] | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556
|  |  |  | 660 | 1660 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe here is the # of projects per year.

## GBF-UNC
GBF-UNC - Unconstrained scenario, with 33% GBF Foundations.
Year
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTALS
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
| TURBINES ORDERED, MW | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 0 | 2370.6617
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 419.095
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 568.5446 | 177.8333 | 240.2486 | 154 |  |  | 1257.285
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 419.095
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 419.095
FOUNDATIONS
1 | Monopiles (turbine) | 14.1138 | 111.6442 | 88.3892 | 73.172 | 63.9012 | 117.0365 | 56.342 | 96.9966 | 12.8324 | 62.5399 | 19.5617 | 26.4273 | 16.94 |  |  | 759.897
1 | Transition Piece | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  |  | 767.5727
1 | Jackets (turbine) | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  |  | 767.5727
1 | GBF (turbine) | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  |  | 767.5727
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  |  | 71
SUBSTATIONS
2 | OSS Topsides | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 0 |  |  | 63
CABLES
1 | Array cable, km | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 |  |  | 6073.3296
1 | Export cable, km | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 |  |  | 6559.2332
TRANSPORT
| TURBINES, MW | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 2370.6617
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 419.095
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 568.5446 | 177.8333 | 240.2486 | 154 |  | 1257.285
NACELLES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 419.095
TOWERS, m
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 419.095
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 14.1138 | 111.6442 | 88.3892 | 73.172 | 63.9012 | 117.0365 | 56.342 | 96.9966 | 12.8324 | 62.5399 | 19.5617 | 26.4273 | 16.94 |  | 759.897
1 | Transition Piece | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111
1 | Jackets (turbine) | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  | 767.5727
1 | GBF (turbine) | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  | 767.5727
1 | Jacket (Substation) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  | 71
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 |  | 65
CABLES
1 | Array cable, km | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 |  | 6073.3296
1 | Export cable, km | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 |  | 6559.2332
VESSELS
0
0
NOTE: This table is the FOUNDATION, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 20592.332 | 22886.332 | 27615.2697 | 28315.2204 | 31726.4882 | 32793.4882 | 34234.9798 | 35158.9798 | 35158.9798
| Installed MW |  | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 5625.9938 | 2294 | 4728.9377 | 699.9506 | 3411.2678 | 1067 | 1441.4916 | 924 | 35158.9798
| Number of Projects |  | 0 | 2 | 6 | 5 | 6 | 3 | 7 | 3 | 6 | 1 | 3 | 1 | 2 | 1 | 46
| TURBINES, MW | 0 | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2370.6617
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 419.095
ROTOR BLADES, UNITS
| 12 |  | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 | 4196.4693
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6584 | 568.5446 | 177.8333 | 240.2486 | 154 | 1257.285
NACELLES, MW
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 419.095
TOWERS, UNITS
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 419.095
| FOUNDATIONS |  | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 170.7333 | 293.9292 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2302.7181
33% | Monopiles (turbine) |  | 0 | 14.1138 | 111.6442 | 88.3892 | 73.172 | 63.9012 | 117.0365 | 56.342 | 96.9966 | 12.8324 | 62.5399 | 19.5617 | 26.4273 | 16.94 | 759.897
33.33% | Transition Piece |  | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 | 767.5727
33.33% | GBF (turbine) |  | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 | 767.5727
33.33% | Jacket (turbine) |  | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 | 767.5727
| Jacket (Substation) |  | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 | 71
SUBSTATIONS
| OSS Topside |  |  | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 65
CABLES, KM
| Array cable, km |  |  | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 | 6073.3296
| Export cable, km |  |  | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 | 6559.2332
VESSELS, (Vessel.Day)
| WTIV (12 MW) |  | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 562.5994 | 229.4 | 472.8938 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3292 | 284.2723 | 88.9167 | 120.1243 | 77
| HLV/WTIV (foundation) |  | 0 | 42.5554 | 336.6243 | 266.5069 | 220.6247 | 192.6718 | 352.8827 | 169.8797 | 292.4595 | 38.6917 | 188.5673 | 58.9814 | 79.6825 | 51.0767
| WTIV Total Days |  |  | 106.7092 | 844.0981 | 701.2762 | 586.2247 | 483.1318 | 915.4821 | 399.2797 | 765.3533 | 97.0209 | 472.8396 | 147.8981 | 199.8068 | 128.0767
| HLV (Substation) |  | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 50 | 80 | 10 | 60 | 20 | 30 | 20
| CLV |  | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 837.9105 | 432.5255 | 766.5352 | 93.0985 | 588.3139 | 181.5435 | 251.0667 | 166.182
| Rock damping |  | 0 | 21.1708 | 167.4664 | 132.5838 | 109.758 | 95.8518 | 175.5547 | 84.513 | 145.4949 | 19.2486 | 93.8099 | 29.3425 | 39.641 | 25.41
VESSELS, (Vessels needed)
| WTIV (12 MW) |  | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 5 | 5 | 4 | 3 | 5 | 2 | 4 | 2 | 3 | 2 | 2 | 2
|  |  |  | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| feeder Barges |  | 0 | 4 | 10 | 10 | 8 | 6 | 10 | 4 | 8 | 4 | 6 | 4 | 4 | 4
| CTV |  | 0 | 6 | 18 | 26 | 32 | 33 | 41 | 44 | 49 | 48 | 48 | 49 | 50 | 51 | 51
| CLV |  | 0 | 1 | 4 | 3 | 3 | 2 | 4 | 2 | 4 | 1 | 3 | 1 | 2 | 1 | 0
| Rock damping vessel |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe here is the # of projects per year.

## WC-UNC
Toggle
OUTPUT -WEST COAST UNCONSTRAINED DEMAND PIPELINE scenario
1. link procurement timelines in column A (one for each item)
[16 empty] | WC-Undeveloped | 1 | 2. copy/paste from cell C10 into new row
|  | Year | [15 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 |  |  | 166.6667
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 |  |  | 27.7778
ROTOR BLADES, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 100 | 200 | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 500
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 0 | 0 | 0 | 0 |  |  | 83.3333
NACELLES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 |  |  | 166.6667
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 |  |  | 27.7778
TOWERS, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 |  |  | 166.6667
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 |  |  | 27.7778
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | Transition Piece | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | Jackets (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | GBF (turbine) | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0 |  |  | 194.4444
1 | Jacket (Substation) | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 |  |  | 6
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 6
CABLES
1 | Array cable, km | 0 | 0 | 0 | 0 | 0 | 122 | 244 | 244 | 101.6667 | 0 | 0 | 0 | 0 |  |  | 711.6667
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 105 | 0 | 0 | 0 | 0 |  |  | 645
| Total Turbines | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0 | 0 | 0 | 194.4444
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 |  | 166.6667
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 |  | 27.7778
ROTOR BLADES, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 200 | 200 | 0 | 0 | 0 | 0 | 0 |  | 500
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 0 | 0 | 0 | 0 |  | 83.3333
NACELLES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 |  | 166.6667
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 |  | 27.7778
TOWERS, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 |  | 166.6667
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 |  | 27.7778
FOUNDATIONS
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | Floating (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0 |  | 194.4444
1 | Floating (floating OSS) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 |  | 6
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 |  | 6
CABLES
1 | Array cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 244 | 244 | 101.6667 | 0 | 0 | 0 | 0 |  | 711.6667
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 105 | 0 | 0 | 0 | 0 |  | 645
| Total Turbines | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0 | 0 | 194.4444
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1500 | 2500 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
| Installed MW |  | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 1000 | 500 | 0 | 0 | 0 | 0 | 3000
| Projects Constructed |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 6
| TURBINES (total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0 | 194.4444
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 | 166.6667
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 | 27.7778
ROTOR BLADES
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 500
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 0 | 0 | 0 | 0 | 83.3333
NACELLES
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 | 166.6667
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 | 27.7778
TOWERS
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 | 166.6667
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.7778 | 0 | 0 | 0 | 0 | 27.7778
| FOUNDATIONS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Floating (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0 | 194.4444
| Floating (floating OSS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 6
SUBSTATIONS
| Floating OSS Topside |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 6
CABLES, KM
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 244 | 244 | 101.6667 | 0 | 0 | 0 | 0
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 105 | 0 | 0 | 0 | 0
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Mob/demob time to be added
| WTIV (15 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 0 | 0 | 0 |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 100 | 41.6667 | 0 | 0 | 0 | 0
| WTIV total days |  |  | 0 | 0 | 0 | 0 | 0 | 100 | 200 | 200 | 83.3333 | 0 | 0 | 0 | 0
| HLV (Substation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 10 | 0 | 0 | 0 | 0
| CLV |  | 0 | 0 | 0 | 0 | 0 | 0 | 106.5 | 203.5 | 203.5 | 97.6667 | 0 | 0 | 0 | 0
| Rock dumping |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VESSELS
| WTIV (12 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| HLV/WTIV (foundation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Total WTIV |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| HLV (Substation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Feeder Barges |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
| CTV |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 11 | 11 | 9 | 8 | 8 | 8 | 8
| CLV |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Rock dumping vessel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
| WC Lay-down Area (acres) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 0 | 0 | 0 | 0
| Total Turbines |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0 | 194.4444
Note on B116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe Can you please adjust this for the floating WC projects? Same for the HLV for floating substation (row 118). That is, to reflect any difference in how WTIVs will be used (or not) to install floating projects. Thanks!
Note on J136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe the port requirements for Berth are keyed to the # of WTIVs, but should it be keyed to # of barges? Or is is assumed that barges will be circulating so we don't need quite as many berths as we have barges? What's your assumption here? Also, I rounded up to whole numbers bc it seems to me a 1/2 of a berth isn't that useful, but again, maybe you have a different thought about what this number means (as in, if it's time-based)?
Note on B137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe Do you have an idea of what the laydown area should be for FOW projects? I assume larger area may be needed -- since the foundations are generally taking up more room (maybe)?? Please update my WAG.

## TOTAL-UNC
Toggle
| OUTPUT - UNCONSTRAINED TOTAL DEMAND PIPELINE (EC and WC) scenario | [14 empty] | EC-UNCONSTRAINED | 1
1. link procurement timelines in column A (one for each item)
[16 empty] | WC-UNCONSTRAINED | 1 | 2. copy/paste from cell C10 into new row
|  | Year | [15 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.4898
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 446.8728
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.1988 | 658.8 | 1145.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 4696.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199.9918 | 568.5446 | 177.8333 | 240.2486 | 154 |  |  | 1340.6183
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.4898
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 446.8728
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.4898
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 446.8728
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  |  | 1504.4034
1 | Transition Piece | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  |  | 1504.4034
1 | Jackets (turbine) | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 |  |  | 277.2762
1 | GBF (turbine) | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  |  | 521.0385
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  |  | 71
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 6
CABLES
1 | Array cable, km | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 |  |  | 65
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 |  |  | 6
| Total Turbines | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.3996 | 219.6 | 381.9292 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 0 | 2565.1061
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 |  | 1565.4898
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 446.8728
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.1988 | 658.8 | 1145.7875 | 0 | 0 | 0 | 0 | 0 |  | 4696.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199.9918 | 568.5446 | 177.8333 | 240.2486 | 154 |  | 1340.6183
NACELLES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 |  | 1565.4898
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 446.8728
TOWERS, m
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 |  | 1565.4898
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 446.8728
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  | 1504.4034
1 | Transition Piece | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667
1 | Jackets (turbine) | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 |  | 277.2762
1 | GBF (turbine) | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  | 521.0385
1 | Jacket (Substation) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  | 71
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 |  | 6
CABLES
1 | Array cable, km | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 |  | 65
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 |  | 6
| Total Turbines | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.3996 | 219.6 | 381.9292 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 2565.1061
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 21092.332 | 24386.332 | 30115.2697 | 31315.2204 | 34726.4882 | 35793.4882 | 37234.9798 | 38158.9798 | 38158.9798
| Installed MW |  | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 6125.9938 | 3294 | 5728.9377 | 1199.9506 | 3411.2678 | 1067 | 1441.4916 | 924 | 38158.9798
| Projects Constructed |  | 0 | 2 | 6 | 5 | 6 | 3 | 8 | 5 | 8 | 2 | 3 | 1 | 2 | 1 | 52
| TURBINES (total) | 0 | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.3996 | 219.6 | 381.9292 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2565.1061
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 | 1565.4898
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 446.8728
ROTOR BLADES
| 12 |  | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.1988 | 658.8 | 1145.7875 | 0 | 0 | 0 | 0 | 0 | 4696.4693
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199.9918 | 568.5446 | 177.8333 | 240.2486 | 154 | 1340.6183
NACELLES
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 | 1565.4898
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 446.8728
TOWERS
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 219.6 | 381.9292 | 0 | 0 | 0 | 0 | 0 | 1565.4898
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6639 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 446.8728
| FOUNDATIONS |  | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 170.7333 | 293.9292 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2302.7181
| Monopiles (turbine) |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 | 1504.4034
| Transition Piece |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 | 1504.4034
| GBF (turbine) |  | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 | 277.2762
| Jacket (turbine) |  | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 | 521.0385
| Jacket (OSS) |  | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 | 71
| Floating (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 27.7778 | 0 | 0 | 0 | 0 | 194.4444
| Floating (floating OSS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 6
SUBSTATIONS
| Fixed OSS Topside |  | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 65
| Floating OSS Topside |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 6
CABLES, KM
| Static Array Cable, km |  | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 1004.9767 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 | 6742.4646
| Static Export Cable, km |  | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 | 6559.2332
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 244 | 244 | 101.6667 | 0 | 0 | 0 | 0 | 711.6667
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 105 | 0 | 0 | 0 | 0 | 645
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Mob/demob time to be added
| WTIV (15 MW) |  | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 612.5994 | 329.4 | 572.8938 | 0 | 0 | 0 | 0 | 0 |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.9959 | 284.2723 | 88.9167 | 120.1243 | 77 |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 463.7595 | 383.7692 | 316.1 | 290.46 | 453.0507 | 204.9 | 440.8938 | 58.3292 | 173.7612 | 59.2778 | 91.2076 | 38.5
| WTIV total days |  |  | 128.3077 | 971.2334 | 818.5385 | 681.7 | 580.92 | 1065.65 | 534.3 | 1013.7875 | 158.3251 | 458.0335 | 148.1944 | 211.3319 | 115.5
| HLV (Substation) |  | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 50 | 80 | 10 | 60 | 20 | 30 | 20
| CLV |  | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 883.9105 | 689.8092 | 856.5352 | 137.0985 | 588.3139 | 181.5435 | 251.0667 | 166.182
| Rock dumping |  | 0 | 49.1538 | 344.2403 | 269.2596 | 241.1 | 135.1 | 320.9873 | 204.9 | 373.6188 | 58.3292 | 129.4862 | 29.6389 | 62.291 | 38.5
VESSELS
| WTIV (12 MW) |  | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 2 | 2 | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 5 | 5 | 5 | 4 | 7 | 4 | 6 | 4 | 3 | 2 | 2 | 2
|  |  | 0 | 1 | 4 | 4 | 3 | 3 | 6 | 3 | 5 | 2 | 2 | 1 | 1 | 1
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
| Feeder Barges |  | 0 | 4 | 10 | 10 | 10 | 8 | 14 | 8 | 12 | 8 | 6 | 4 | 4 | 4
| CTV |  | 0 | 6 | 18 | 26 | 32 | 33 | 45 | 52 | 60 | 59 | 57 | 57 | 58 | 59 | 59
| CLV |  | 0 | 1 | 4 | 3 | 3 | 2 | 5 | 3 | 5 | 2 | 3 | 1 | 2 | 1
| Rock dumping vessel |  | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) |  | 0 | 3 | 8 | 8 | 8 | 6 | 11 | 6 | 9 | 6 | 5 | 3 | 3 | 3
| EC Lay-down Area (acres) |  | 0 | 29 | 116 | 116 | 87 | 87 | 145 | 58 | 116 | 29 | 58 | 29 | 29 | 29
| WC Lay-down Area (acres) |  | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 0 | 0 | 0 | 0

## ACCEL
Toggle
| OUTPUT - ACCELERATED TOTAL DEMAND PIPELINE (EC AND WC) scenario | [14 empty] | EC-ACCEL | 1
1. link procurement timelines in column A (one for each item)
[16 empty] | WC-ACCEL | 1 |  | 2. copy/paste from cell C10 into new row
|  | Year | [16 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL |  | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 |  |  | 1847.4264
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 |  |  | 1840.5538
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.1988 | 1325.1988 | 1325.1988 | 0 | 0 | 0 | 0 | 0 |  |  | 5542.2793
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104.3323 | 1104.3323 | 1104.3323 | 1104.3323 | 1104.3323 |  |  | 5521.6615
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 |  |  | 1847.4264
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 |  |  | 1840.5538
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 |  |  | 1847.4264
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 |  |  | 1840.5538
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 |  |  | 2404.5016
1 | Transition Piece | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 |  |  | 2404.5016
1 | Jackets (turbine) | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 |  |  | 473.1206
1 | GBF (turbine) | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 |  |  | 1023.9303
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 97
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  | 15
CABLES
1 | Array cable, km | 2 | 10 | 6 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 94
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 15
| Total Turbines | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 0 | 0 | 4240.7239
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 |  | 1847.4264
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 |  | 1840.5538
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.1988 | 1325.1988 | 1325.1988 | 0 | 0 | 0 | 0 | 0 |  | 5542.2793
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104.3323 | 1104.3323 | 1104.3323 | 1104.3323 | 1104.3323 |  | 5521.6615
NACELLES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 |  | 1847.4264
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 |  | 1840.5538
TOWERS, m
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 |  | 1847.4264
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 |  | 1840.5538
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 |  | 2404.5016
1 | Transition Piece | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916
1 | Jackets (turbine) | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 |  | 473.1206
1 | GBF (turbine) | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 |  | 1023.9303
1 | Jacket (Substation) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 97
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 15
CABLES
1 | Array cable, km | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 94
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 15
| Total Turbines | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 0 | 4240.7239
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 21092.332 | 27718.3259 | 34344.3197 | 40970.3136 | 47596.3074 | 54222.3012 | 60848.2951 | 67474.2889 | 67474.2889
| Installed MW |  | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 6125.9938 | 6625.9938 | 6625.9938 | 6625.9938 | 6625.9938 | 6625.9938 | 6625.9938 | 6625.9938 | 67474.2889
| Projects Constructed |  | 0 | 2 | 6 | 5 | 6 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 86
| TURBINES (total) |  |  | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 4240.7239
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 | 1847.4264
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 1840.5538
ROTOR BLADES
| 12 |  | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.1988 | 1325.1988 | 1325.1988 | 0 | 0 | 0 | 0 | 0 | 5542.2793
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104.3323 | 1104.3323 | 1104.3323 | 1104.3323 | 1104.3323 | 5521.6615
NACELLES
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 | 1847.4264
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 1840.5538
TOWERS
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 0 | 0 | 0 | 0 | 0 | 1847.4264
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 1840.5538
| FOUNDATIONS |  | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 354.656 | 354.656 | 354.656 | 354.656 | 354.656 | 354.656 | 354.656 | 3901.5526
| Monopiles (turbine) |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 2404.5016
| Transition Piece |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 2404.5016 | 0.61629
| GBF (turbine) |  | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 473.1206 | 0.12126
| Jacket (turbine) |  | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 1023.9303 | 0.26244
| Jacket (OSS) |  | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 97
| Floating (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.3333 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 500
| Floating (floating OSS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 15
SUBSTATIONS
| Fixed OSS Topside |  | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 94
| Floating OSS Topside |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 15
CABLES, KM
| Static Array Cable, km |  | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 10691.0804
| Static Export Cable, km |  | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 7981.915
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 244 | 244 | 244 | 244 | 244 | 244 | 244 | 1830
| Dynamic Export Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 210 | 210 | 210 | 210 | 210 | 1590
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Mob/demob time to be added
| WTIV (15 MW) |  | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 612.5994 | 662.5994 | 662.5994 | 0 | 0 | 0 | 0 | 0 |  |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.1662 | 552.1662 | 552.1662 | 552.1662 | 552.1662 |  |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 463.7595 | 383.7692 | 316.1 | 290.46 | 453.0507 | 453.0507 | 453.0507 | 453.0507 | 453.0507 | 453.0507 | 453.0507 | 453.0507
| WTIV total days |  |  | 128.3077 | 971.2334 | 818.5385 | 681.7 | 580.92 | 1065.65 | 1115.65 | 1115.65 | 1005.2168 | 1005.2168 | 1005.2168 | 1005.2168 | 1005.2168
| HLV (Substation) |  | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
| CLV |  | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 883.9105 | 907.9105 | 907.9105 | 907.9105 | 907.9105 | 907.9105 | 907.9105 | 907.9105
| Rock dumping |  | 0 | 49.1538 | 344.2403 | 269.2596 | 241.1 | 135.1 | 320.9873 | 320.9873 | 320.9873 | 320.9873 | 320.9873 | 320.9873 | 320.9873 | 320.9873
VESSELS
| WTIV (12 MW) |  | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3
| HLV/WTIV (foundation) |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Total WTIV |  | 0 | 2 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  |  | 1 | 4 | 4 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Feeder Barges |  | 0 | 4 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| CTV |  | 0 | 6 | 18 | 26 | 32 | 33 | 43 | 56 | 64 | 72 | 80 | 88 | 96 | 104 | 104
| CLV |  | 0 | 1 | 4 | 3 | 3 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Rock dumping vessel |  | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) |  | 0 | 3 | 8 | 8 | 8 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| EC Lay-down Area (acres) | 0 | 0 | 29 | 116 | 116 | 87 | 87 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145
WC Lay-down Area (acres)
| Total Turbines |  | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.3996 | 441.7329 | 441.7329 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 368.1108 | 4240.7239

## Maps
Scroll down to see the names of the Projects and Call Areas.