## Introduction
Title of related report: | U.S. East Coast and West Coast Offshore Wind Project Pipeline Including Vessels and Port Study
Doc. File Name: | DRAFT US OSW EC-WC Pipeline Gantt Charts 20220113.xlsx
Date: | 2022-01-13
Author: | Ruth Heffernan Marsh, Principal Engineer/PM, DNV
This workbook presents Gantt charts showing the projected U.S. Offshore wind project pipeline through 2035 for a number of development scenarios. The worksheets are described below.
Worksheet name | worksheet description
Assumptions | All assumptions used in this analysis are presented here.
Aggregated | This sheet represents the aggregated information from all projects, undeveloped lease areas, and Wind Energy Areas that are included in this study.
TOTAL-UNC | Gantt chart for the unconstrained project TOTAL pipeline scenario, EAST and WEST COAST. This scenario assumes there are no constraints on supply of any components nor of vessels to complete projects installations. CODs are either those published by the developer or estimated based on available project information.
TOTAL-Expand | Same as TOTAL-UNC plus the addition of FIX-EX and FLOAT-EX
EC-UNC | Gantt chart for the unconstrained project pipeline scenario for the EAST COAST. This scenario assumes there are no constraints on supply of any components nor of vessels to complete projects installations. CODs are either those published by the developer or estimated based on available project information.
WC-UNC | Gantt chart for the unconstrained project pipeline scenario for the WEST COAST. This scenario assumes there are no constraints on supply of any components nor of vessels to complete projects installations. CODs are either those published by the developer or estimated based on available project information.
FIX-EX | Includes additional fixed-bottom lease areas BOEM expects to release after the NY Bight
FLOAT-EX | Includes additional floating lease areas BOEM expects to release after the NY Bight
EC-LOW | Gantt chart for the "low" constrained project pipeline scenario for the EAST COAST. This scenario assumes there are relatively low constraints on turbine supply and vessels needed to complete project installations.
EC-MED | Gantt chart for the "medium" constrained project pipeline scenario for the EAST COAST. This scenario assumes there are relatively low constraints on turbine supply and vessels needed to complete project installations.
EC-HIGH | Gantt chart for the "high" constrained project pipeline scenario for the EAST COAST. This scenario assumes there are relatively low constraints on turbine supply and vessels needed to complete project installations.
GBF-UNC | Gantt chart for the EAST COAST scenario where it is assumed there is equal demand for all three fixed-bottom turbine foundation types (monopile, jacket, and GBF). This scenario assumes there are no constraints on obtaining each foundation type.
ACCEL | Gantt chart for the ACCELERATED project TOTAL pipeline scenario, EAST and WEST COAST. This scenario assumes that once the pipeline reaches it's maximum capacity, the buildout continues at that pace through 2035.

## Assumptions
DESCRIPTION:
This sheet contains ALL project assumptions used in the following worksheets to develop the (GREEN) output sheets, one sheet per scenario
Basic project assumptions are listed in SCRoadmap_scenarios.docx (BOX folder)
KEY:
| Assumptions |  |  |  |  | input
1 | Scenarios |  |  |  |  | calculated
Unconstrained scenario:
| Assumes projects are developed according to Developers' timelines with no constraints on WTG supply and WTIVs. | [10 empty] | Tier 1: finished components
[7 empty] | 8 | Foundations |  |  |  | WTG 12 MW
| Constrained scenarios: | LOW | MED | HIGH | Manuf ramp-up, | % Available for US |  | Type | min depth, m | max depth, m | Notes | WTG 15 MW
| Total MW available for export from Europe, annually | 4000 | 3000 | 2000 | 33% |  |  | Monopile | 0 | 40 | Preferred option (least cost, most used in Europe, simplest, quickest to install). Monopile factory in NJ being constructed by EEW (Orsted). | WTG 18 MW
| Total # of WTIVs available | 9 | 7 | 5 |  | 50% |  | Gravity Base Foundation (GBF) | 20 | 40 | Can be manufactured in US, but more expensive than monopile and jacket (see GBS Foundation sheet). Half of Equinor projects, and half of shallower parts of NY Bight | Monopile
[8 empty] | Jacket | 40 | 60 | Can be manufactured in US | Transition piece
2 | Turbine size (Applied to Undeveloped areas): | [10 empty] | Gravity base
| Turbine Size | sm | med | lg | AVG |  |  | Foundation sensitivity study | % of Total |  |  | Jacket
| COD <= 2026 | 11 | 12 | 13 | 12 |  |  | Monopile | 33.33% |  |  | OSS Jacket
| 2026 < COD <= 2030 | 14 | 15 | 16 | 15 |  |  | Gravity base foundation (GBF) | 33.33% |  |  | Offshore substation
| 2030 < COD <= 2035 | 17 | 18 | 19 | 18 |  |  | Jacket | 33.33% |  |  | Array cables
| Standard development % of Lease Area | 65% | [9 empty] | Export cables
| Build-out lag time for remaining Lease Area | 2 | years
Tier 2: subassemblies
3 | Substations | [5 empty] | 9 | Vessels |  |  |  | Rotor blades: 107m, 115m, 125m
| MW/Substation | 800 | MW |  |  |  |  | Vessel Parameters | Value | Units | Notes | Nacelle: 12MW, 15 MW, 18MW
[8 empty] | Feeder barge min size | 90 | m |  | Tower: 110m, 120m, 130m
4 | Array and Export Cables | [6 empty] | WTIV per turbine | 36 | hr | 48 h too high, might be as low as 24 h
| Array cable margin | 10% | [5 empty] | WTIV per foundation | 36 | hr | 48 h too high
| Distance between turbines, nm | 1 | [5 empty] | HLV, per substation | 240 | hr |  | States
[8 empty] | Scour protection Install vessel, per MP | 36 | hr | incl. re-loading
[8 empty] | Feeder barge transit time | 12 | hr |  | States | Abbrev. | No.
5 | Weather Window | [6 empty] | Feeder barge time on site | 108 | hr |  | Maine | ME | 1
| Quarter | % active time | Notes |  |  |  |  | WTG's per barge | 3 | # |  | New Hampshire | NH | 2
| Q1 | 33.1% | "Red Period" Jan-April no pile-driving due to Right Whale activity |  |  |  |  | Barge mob time | 36 | hr |  | Massachusetts | MA | 3
| Q2 | 66.67% | "Red Period" ends April 30, "Yellow period" May 1-15 | [8 empty] | Rhode Island | RI | 4
| Q3 | 100% | [5 empty] | CTVs | # required | Units | Notes | Connecticut | CT | 5
| Q4 | 66.67% | "Yellow Period" Nov |  |  |  |  | Construction year 0 | 2 | # |  | New York | NY | 6
| Annual construction window, East Coast: | 66.61% | % of year when construction is possible. |  |  |  |  | Year 1 | 2 | # |  | New Jersey | NJ | 7
| Assume Project is installed within one year (during Q2/Q3 weather window) | [6 empty] | Year 2 - 20 | 1 | # |  | Delaware | DE | 8
| Tufts study -- restrictions + weather windows justify 8 month (2/3) ocnstruction window | [6 empty] | initial CTV need | 2 | # | Existing projects (Block island, CVOW demo) | Maryland | MD | 9
[12 empty] | Virginia | VA | 10
6 | Turbine spacing | [6 empty] | Cable-laying vessels | Value | Units | Notes | North Carolina | NC | 11
| One turbine per nm2 | 1 | nm2 |  |  |  |  | Cable Laying speed | 4 | km/day |  | South Carolina | SC | 12
[8 empty] | Mob/demob time | 20 | days |  | California | CA | 13
7 | Procurement, Transport, Construction, Installation Timelines
| Procurement & manufacturing | Duration | Units
| Blades | 1 | yr
| Nacelle | 1 | yr |  |  |  | 10 | Toggle to INCLUDE/EXCLUDE (change these on Annual Gantt Chart sheet)
| Tower | 1 | yr |  |  |  |  | Include Projects | 1
| OSS | 2 | yr |  |  |  |  | Include Undeveloped areas | 1
| Array cables | 1 | yr
| Export cables | 1 | yr
| Monopile | 1 | yr
| GBS foundation | 1 | yr |  |  |  | 11 | Conversions:
| Jacket foundation | 1 | yr |  |  |  |  | Acres per NM^2 | 847.548
| OSS Jacket | 1 | yr |  |  |  |  | km per mile | 1.6093
| Transport & storage | 1 | yr |  |  |  |  | nautical miles per mile | 0.86897
| Start of construction to COD | 1 | yr |  |  |  |  | km per NM | 1.852
[8 empty] | acres per km^2 | 247.1054
[8 empty] | km^2/nm^2 | 3.4299
Other Assumptions:
1 | NY Bight lease areas and Wilmington East WEA are included in analysis | [6 empty] | Floating Wind vessels parameter | Value | Units | Notes
2 | Additional Call Areas and WEAs along the East Coast (e.g., Wilmington West, NC and Grand Strand, SC) not included, due to uncertainty regarding project development | [6 empty] | Towing speed | 4 | kt | tow from WTG integration port to offshore location
3 | CA Humboldt WEA and Morro Bay with East and West extensions CA are included | [6 empty] | Average distance from port | 283.8351 | NM
4 | GoM is not included in the analysis | [6 empty] | Non towing speed | 8 | kt | return
5 | % developable remaining lease areas for existing projects was reduced after discussion with Emily Lindow of BOEM: she anticipates opposition to developing remaining lease areas. | [6 empty] | tug manoeuvering and prep time | 24 | hr | for each WTG
6 | Assumed turbine spacing of 1 WTG per nm2 yields turbine density of 3.5MW/km^2 for 12 MW turbines, which is slightly higher than the NREL 2020 Offhsore Wind Technologies Market Report, up to 5.3MW/km^2 for 18 MW turbines. | [6 empty] | Offshore Tug, per WTG | 130.4381 | hr | tow from WTG integration port to offshore location + return
7 | Spacing of 1 nm between turbines is approximately 8.3 rotor diameters for the largest known rotors (222 m diameter). | [6 empty] | number of mooring sets per mobilization | 3 | #
[8 empty] | Anchor Handling mobilization time | 94.9588 | hr | return to port for loading new mooring lines and back to offshore site
[8 empty] | Anchor Handling Vessel, per WTG | 115.6529 | hr | incl. pre-lay, anchor proof, and hook-up
[8 empty] | Annual construction window, California | 75% | % | % of year when construction is possible.
Floating wind port requirements
[8 empty] | Tack time | 10 | d
[8 empty] | unit per year | 35 | #
[9 empty] | Lay-down area (acres) | Berth length (m)
[8 empty] | Foundation assembly | 35 | 440
[8 empty] | Turbine staging | 25 | 660
[8 empty] | Mooring marshalling | 10 | 150
[8 empty] | TOTAL | 70 | 1250
[8 empty] | requirement (/WTG/yr) | 2 | 35.7143
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: After meeting w/Emily Lindow, Chief of Staff @BOEM, reducing this to 60%, and further reducing the "remaining lease areas" acreage to 30%. She explained that recent conversations with fisheries indicated they would likely oppose projects further building out their lease areas, at least initially. So we can't count on more than an additional 5 GW from those leftover lease areas.

## TOTAL-UNC
Toggle
| OUTPUT - UNCONSTRAINED TOTAL DEMAND PIPELINE (EC and WC) scenario | [14 empty] | EC-UNCONSTRAINED | 1
1. link procurement timelines in column A (one for each item)
[16 empty] | WC-UNCONSTRAINED | 1 | 2. copy/paste from cell C10 into new row
|  | Year | [15 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 |  |  | 574.7274
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 658.8383 | 1145.8258 | 0 | 0 | 0 | 0 | 0 |  |  | 4696.5809
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433.6193 | 651.8337 | 244.4807 | 240.2486 | 154 |  |  | 1724.1823
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 |  |  | 574.7274
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 |  |  | 574.7274
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  |  | 1504.4034
1 | Transition Piece | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  |  | 1504.4034
1 | Jackets (turbine) | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 |  |  | 277.2762
1 | GBF (turbine) | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  |  | 521.0385
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  |  | 71
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 |  |  | 9
CABLES
1 | Array cable, km | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 |  |  | 65
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  |  | 9
| Total Turbines | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 | 0 | 0 | 2692.998
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 |  | 574.7274
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 658.8383 | 1145.8258 | 0 | 0 | 0 | 0 | 0 |  | 4696.5809
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433.6193 | 651.8337 | 244.4807 | 240.2486 | 154 |  | 1724.1823
NACELLES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 |  | 574.7274
TOWERS, m
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 |  | 574.7274
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  | 1504.4034
1 | Transition Piece | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667
1 | Jackets (turbine) | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 |  | 277.2762
1 | GBF (turbine) | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  | 521.0385
1 | Jacket (Substation) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  | 71
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  | 9
CABLES
1 | Array cable, km | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 |  | 65
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  | 9
| Total Turbines | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 | 0 | 2692.998
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 21092.5073 | 24386.6985 | 30115.8275 | 32717.5435 | 36628.5459 | 38095.4298 | 39536.9215 | 40460.9215 | 40460.9215
| Installed MW |  | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 6126.169 | 3294.1913 | 5729.129 | 2601.716 | 3911.0024 | 1466.884 | 1441.4916 | 924 | 40460.9215
| Projects Constructed |  | 0 | 2 | 6 | 5 | 6 | 3 | 8 | 5 | 8 | 4 | 4 | 2 | 2 | 1 | 56
| TURBINES (total) | 0 | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 | 2692.998
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 | 1565.527
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 | 574.7274
ROTOR BLADES
| 12 |  | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 658.8383 | 1145.8258 | 0 | 0 | 0 | 0 | 0 | 4696.5809
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433.6193 | 651.8337 | 244.4807 | 240.2486 | 154 | 1724.1823
NACELLES
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 | 1565.527
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 | 574.7274
TOWERS
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 | 1565.527
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.5398 | 217.2779 | 81.4936 | 80.0829 | 51.3333 | 574.7274
| FOUNDATIONS |  | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 170.7333 | 293.9292 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2302.7181
| Monopiles (turbine) |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 | 1504.4034
| Transition Piece |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 | 1504.4034
| GBF (turbine) |  | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 | 277.2762
| Jacket (turbine) |  | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 | 521.0385
| Jacket (OSS) |  | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 | 71
| Floating (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 277.7703
| Floating (floating OSS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 9
SUBSTATIONS
| Fixed OSS Topside |  | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 65
| Floating OSS Topside |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 9
CABLES, KM
| Static Array Cable, km |  | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 1004.9767 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 | 6742.4646
| Static Export Cable, km |  | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 | 6559.2332
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 122.0428 | 244.0467 | 244.0467 | 223.5809 | 101.6127 | 81.3097 | 0 | 0 | 1016.6394
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 205 | 105 | 105 | 0 | 0 | 955
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Mob/demob time to be added
| WTIV (15 MW) |  | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 612.6169 | 329.4191 | 572.9129 | 0 | 0 | 0 | 0 | 0 |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.8097 | 325.9169 | 122.2403 | 120.1243 | 77 |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 463.7595 | 383.7692 | 316.1 | 290.46 | 453.0507 | 204.9 | 440.8938 | 58.3292 | 173.7612 | 59.2778 | 91.2076 | 38.5
| WTIV total days |  |  | 128.3077 | 971.2334 | 818.5385 | 681.7 | 580.92 | 1065.6676 | 534.3191 | 1013.8067 | 275.1389 | 499.678 | 181.5181 | 211.3319 | 115.5
| HLV (Substation) |  | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 50 | 80 | 10 | 60 | 20 | 30 | 20
| CLV |  | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 883.9105 | 689.8092 | 856.5352 | 249.0985 | 632.3139 | 221.5435 | 251.0667 | 166.182
| Rock dumping |  | 0 | 49.1538 | 344.2403 | 269.2596 | 241.1 | 135.1 | 320.9873 | 204.9 | 373.6188 | 58.3292 | 129.4862 | 29.6389 | 62.291 | 38.5
VESSELS
| WTIV (12 MW) |  | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 5 | 5 | 5 | 4 | 5 | 2 | 4 | 2 | 3 | 2 | 2 | 2
|  |  |  | 1 | 4 | 4 | 3 | 3 | 5 | 3 | 5 | 2 | 3 | 1 | 1 | 1
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Feeder Barges |  | 0 | 4 | 10 | 10 | 10 | 8 | 10 | 4 | 8 | 4 | 6 | 4 | 4 | 4
| CTV |  | 0 | 6 | 18 | 26 | 32 | 33 | 43 | 50 | 58 | 61 | 61 | 61 | 61 | 61 | 61
| SOV |  | 0 | 2 | 8 | 13 | 19 | 22 | 30 | 35 | 43 | 47 | 51 | 53 | 55 | 56 | 56
| CLV |  | 0 | 1 | 4 | 3 | 3 | 2 | 4 | 3 | 4 | 2 | 3 | 1 | 2 | 1
| scour protection vessel |  | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) |  | 0 | 3 | 8 | 8 | 8 | 6 | 8 | 3 | 6 | 3 | 5 | 3 | 3 | 3
| EC Lay-down Area (acres) |  | 0 | 40 | 160 | 160 | 120 | 120 | 200 | 80 | 160 | 40 | 80 | 40 | 40 | 40
| WC Lay-down Area (acres) |  | 0 | 0 | 0 | 0 | 0 | 0 | 66.69 | 133.3588 | 133.3588 | 122.1753 | 55.5261 | 44.4316 | 0 | 0

## TOTAL-Expand
[16 empty] | EC-UNCONSTRAINED | 1 | Toggle
| OUTPUT - UNCONSTRAINED TOTAL DEMAND PIPELINE (EC and WC) scenario | [14 empty] | WC-UNCONSTRAINED | 1
[16 empty] | FIX-EX | 1 |  | 1. link procurement timelines in column A (one for each item)
[16 empty] | FLOAT-EX | 1 |  | 2. copy/paste from cell C10 into new row
|  | Year | [16 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL |  | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 |  |  | 1006.2979
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 658.8383 | 1145.8258 | 0 | 0 | 0 | 0 | 0 |  |  | 4696.5809
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558.6193 | 651.8337 | 539.192 | 740.2486 | 529 |  |  | 3018.8936
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 |  |  | 1006.2979
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 |  |  | 1006.2979
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 269.9125 | 38.8861 | 131.4427 | 19.7593 | 41.5273 | 91.6186 |  |  | 1636.3072
1 | Transition Piece | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 269.9125 | 38.8861 | 131.4427 | 19.7593 | 41.5273 | 91.6186 |  |  | 1636.3072
1 | Jackets (turbine) | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 20.8333 | 0 | 118.7927 | 19.7593 | 19.2778 | 91.6186 |  |  | 409.18
1 | GBF (turbine) | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  |  | 521.0385
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 12 | 1 | 9 | 2 | 3 | 6 |  |  | 79
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 4 | 3 | 0 |  |  | 17
CABLES
1 | Array cable, km | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 2 | 6 | 5 | 3 | 2 |  |  | 69
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 4 | 3 |  |  | 17
| Total Turbines | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 | 0 | 0 | 3124.5684
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 |  | 1006.2979
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 658.8383 | 1145.8258 | 0 | 0 | 0 | 0 | 0 |  | 4696.5809
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558.6193 | 651.8337 | 539.192 | 740.2486 | 529 |  | 3018.8936
NACELLES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 |  | 1006.2979
TOWERS, m
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 |  | 1565.527
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 |  | 1006.2979
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 269.9125 | 38.8861 | 131.4427 | 19.7593 | 41.5273 | 91.6186 |  | 1636.3072
1 | Transition Piece | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 269.9125 | 38.8861 | 131.4427 | 19.7593 | 41.5273 | 91.6186
1 | Jackets (turbine) | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 20.8333 | 0 | 118.7927 | 19.7593 | 19.2778 | 91.6186 |  | 409.18
1 | GBF (turbine) | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  | 521.0385
1 | Jacket (Substation) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 12 | 1 | 9 | 2 | 3 | 6 |  | 79
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 4 | 3 |  | 17
CABLES
1 | Array cable, km | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 2 | 6 | 5 | 3 | 2 |  | 69
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 4 | 3 |  | 17
| Total Turbines | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 | 0 | 3124.5684
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 21092.5073 | 24386.6985 | 30115.8275 | 33467.5435 | 37378.5459 | 40613.6977 | 45055.1893 | 48229.1893 | 48229.1893
| Installed MW |  | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 6126.169 | 3294.1913 | 5729.129 | 3351.716 | 3911.0024 | 3235.1518 | 4441.4916 | 3174 | 48229.1893
| Projects Constructed |  | 0 | 2 | 6 | 5 | 6 | 3 | 8 | 5 | 8 | 5 | 4 | 4 | 4 | 3 | 63
| TURBINES (total) | 0 | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 | 3124.5684
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 | 1565.527
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 | 1006.2979
ROTOR BLADES
| 12 |  | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 658.8383 | 1145.8258 | 0 | 0 | 0 | 0 | 0 | 4696.5809
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558.6193 | 651.8337 | 539.192 | 740.2486 | 529 | 3018.8936
NACELLES
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 | 1565.527
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 | 1006.2979
TOWERS
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 219.6128 | 381.9419 | 0 | 0 | 0 | 0 | 0 | 1565.527
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.2064 | 217.2779 | 179.7307 | 246.7495 | 176.3333 | 1006.2979
| FOUNDATIONS |  | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 170.7333 | 335.5958 | 38.8861 | 279.752 | 59.2778 | 80.0829 | 183.2371 | 2566.5257
| Monopiles (turbine) |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 269.9125 | 38.8861 | 131.4427 | 19.7593 | 41.5273 | 91.6186 | 1636.3072
| Transition Piece |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 269.9125 | 38.8861 | 131.4427 | 19.7593 | 41.5273 | 91.6186 | 1636.3072
| GBF (turbine) |  | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 20.8333 | 0 | 118.7927 | 19.7593 | 19.2778 | 91.6186 | 409.18
| Jacket (turbine) |  | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 | 521.0385
| Jacket (OSS) |  | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 12 | 1 | 9 | 2 | 3 | 6 | 79
| Floating (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 30.2158 | 166.6667 | 125 | 577.437
| Floating (floating OSS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 4 | 3 | 17
SUBSTATIONS
| Fixed OSS Topside |  | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 2 | 6 | 5 | 3 | 2 | 69
| Floating OSS Topside |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 4 | 3 | 17
CABLES, KM
| Static Array Cable, km |  | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 176.894 | 622.8507 | 328.3347 | 175.862 | 112.728 | 6362.9902
| Static Export Cable, km |  | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 213 | 802.405 | 750 | 372.405 | 280 | 7159.2332
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 122.0428 | 244.0467 | 244.0467 | 223.5809 | 101.6127 | 110.5897 | 610 | 457.5 | 2113.4194
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 205 | 105 | 205 | 440 | 320 | 1815
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Mob/demob time to be added
| WTIV (15 MW) |  | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 612.6169 | 329.4191 | 572.9129 | 0 | 0 | 0 | 0 | 0 |  |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279.3097 | 325.9169 | 269.596 | 370.1243 | 264.5 |  |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 463.7595 | 383.7692 | 316.1 | 290.46 | 453.0507 | 204.9 | 472.1438 | 58.3292 | 241.439 | 59.2778 | 91.2076 | 137.4278
| WTIV total days |  |  | 128.3077 | 971.2334 | 818.5385 | 681.7 | 580.92 | 1065.6676 | 534.3191 | 1045.0567 | 337.6389 | 567.3558 | 328.8738 | 461.3319 | 401.9278
| HLV (Substation) |  | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 50 | 80 | 20 | 60 | 50 | 30 | 20
| CLV |  | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 883.9105 | 522.5255 | 856.5352 | 365.4735 | 632.3139 | 511.5837 | 441.0667 | 318.182
| Rock dumping |  | 0 | 49.1538 | 344.2403 | 269.2596 | 241.1 | 135.1 | 320.9873 | 204.9 | 404.8688 | 58.3292 | 197.164 | 29.6389 | 62.291 | 137.4278
VESSELS
| WTIV (12 MW) |  | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1
| Total WTIV |  | 0 | 2 | 5 | 5 | 5 | 4 | 5 | 2 | 4 | 4 | 3 | 4 | 2 | 2
|  |  |  | 1 | 4 | 4 | 3 | 3 | 5 | 3 | 5 | 2 | 3 | 2 | 2 | 2
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Feeder Barges |  | 0 | 4 | 10 | 10 | 10 | 8 | 10 | 4 | 8 | 8 | 6 | 8 | 4 | 4
| CTV |  | 0 | 6 | 18 | 26 | 32 | 33 | 43 | 50 | 58 | 63 | 63 | 66 | 70 | 72 | 72
| SOV |  | 0 | 2 | 8 | 13 | 19 | 22 | 30 | 35 | 43 | 48 | 52 | 56 | 60 | 63 | 63
| CLV |  | 0 | 1 | 4 | 3 | 3 | 2 | 4 | 3 | 4 | 2 | 3 | 3 | 2 | 2
| scour protection vessel |  | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) |  | 0 | 3 | 8 | 8 | 8 | 6 | 8 | 3 | 6 | 6 | 5 | 6 | 3 | 3
| EC Lay-down Area (acres) |  | 0 | 40 | 160 | 160 | 120 | 120 | 200 | 80 | 160 | 40 | 80 | 40 | 40 | 40
| WC Lay-down Area (acres) |  | 0 | 0 | 0 | 0 | 0 | 0 | 66.69 | 133.3588 | 133.3588 | 122.1753 | 55.5261 | 44.4316 | 0 | 0

## EC-UNC
Toggle
| OUTPUT - EAST COAST UNCONSTRAINED DEMAND PIPELINE scenario | [14 empty] | EC-Projects | 1
[16 empty] | EC-Undeveloped | 1 | 1. link procurement timelines in column A (one for each item)
2. copy/paste from cell C10 into new row
|  | Year | [15 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 463.661
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3563 | 568.5446 | 177.8333 | 240.2486 | 154 |  |  | 1390.9829
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 463.661
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 463.661
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  |  | 1504.4034
1 | Transition Piece | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  |  | 1504.4034
1 | Jackets (turbine) | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 |  |  | 277.2762
1 | GBF (turbine) | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  |  | 521.0385
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  |  | 71
SUBSTATIONS
2 | OSS Topsides | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 0 |  |  | 63
CABLES
1 | Array cable, km | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 |  |  | 6073.3296
1 | Export cable, km | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 |  |  | 6559.2332
| Total Turbines | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 0 | 2415.2277
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 463.661
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3563 | 568.5446 | 177.8333 | 240.2486 | 154 |  | 1390.9829
NACELLES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 463.661
TOWERS, m
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 463.661
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 |  | 1504.4034
1 | Transition Piece | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667
1 | Jackets (turbine) | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 |  | 277.2762
1 | GBF (turbine) | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 |  | 521.0385
1 | Jacket (Substation) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  | 71
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 |  | 65
CABLES
1 | Array cable, km | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 |  | 6073.3296
1 | Export cable, km | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 |  | 6559.2332
| Total Turbines | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 2415.2277
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 20592.332 | 22886.332 | 27615.2697 | 29117.4076 | 32528.6754 | 33595.6754 | 35037.1671 | 35961.1671 | 35961.1671
| Installed MW |  | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 5625.9938 | 2294 | 4728.9377 | 1502.1379 | 3411.2678 | 1067 | 1441.4916 | 924 | 35961.1671
| Projects Constructed |  | 0 | 2 | 6 | 5 | 6 | 3 | 7 | 3 | 6 | 2 | 3 | 1 | 2 | 1 | 47
| TURBINES (total) | 0 | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2415.2277
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 463.661
ROTOR BLADES
| 12 |  | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 | 4196.4693
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3563 | 568.5446 | 177.8333 | 240.2486 | 154 | 1390.9829
NACELLES
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 463.661
TOWERS
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 463.661
| FOUNDATIONS |  | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 170.7333 | 293.9292 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2302.7181
| Monopiles (turbine) |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 | 1504.4034
| Transition Piece |  | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 136.6 | 249.0792 | 38.8861 | 86.3241 | 19.7593 | 41.5273 | 25.6667 | 1504.4034
| GBF (turbine) |  | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 | 277.2762
| Jacket (turbine) |  | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 0 | 44.85 | 0 | 29.5167 | 19.7593 | 19.2778 | 0 | 521.0385
| Jacket (OSS) |  | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 | 71
SUBSTATIONS
| OSS Topside |  | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 65
CABLES, KM
| Static Array Cable, km |  | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 | 6073.3296
| Static Export Cable, km |  | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 | 6559.2332
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Mob/demob time to be added
| WTIV (15 MW) |  | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 562.5994 | 229.4 | 472.8938 | 0 | 0 | 0 | 0 | 0 |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125.1782 | 284.2723 | 88.9167 | 120.1243 | 77 |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 463.7595 | 383.7692 | 316.1 | 290.46 | 453.0507 | 204.9 | 440.8938 | 58.3292 | 173.7612 | 59.2778 | 91.2076 | 38.5
| WTIV total days |  |  | 128.3077 | 971.2334 | 818.5385 | 681.7 | 580.92 | 1015.65 | 434.3 | 913.7875 | 183.5074 | 458.0335 | 148.1944 | 211.3319 | 115.5
| HLV (Substation) |  | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 50 | 80 | 10 | 60 | 20 | 30 | 20
| CLV |  | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 837.9105 | 432.5255 | 766.5352 | 153.0985 | 588.3139 | 181.5435 | 251.0667 | 166.182
| Rock dumping |  | 0 | 49.1538 | 344.2403 | 269.2596 | 241.1 | 135.1 | 320.9873 | 204.9 | 373.6188 | 58.3292 | 129.4862 | 29.6389 | 62.291 | 38.5
VESSELS
| WTIV (12 MW) |  | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 5 | 5 | 5 | 4 | 5 | 2 | 4 | 2 | 3 | 2 | 2 | 2
|  |  |  | 1 | 4 | 4 | 3 | 3 | 5 | 2 | 4 | 1 | 2 | 1 | 1 | 1
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Feeder Barges |  | 0 | 4 | 10 | 10 | 10 | 8 | 10 | 4 | 8 | 4 | 6 | 4 | 4 | 4
| CTV |  | 0 | 6 | 18 | 26 | 32 | 33 | 41 | 44 | 49 | 50 | 50 | 50 | 51 | 52 | 52
| SOV |  | 0 | 2 | 8 | 13 | 19 | 22 | 29 | 32 | 38 | 40 | 43 | 44 | 46 | 47 | 47
| CLV |  | 0 | 1 | 4 | 3 | 3 | 2 | 4 | 2 | 4 | 1 | 3 | 1 | 2 | 1
| scour protection vessel |  | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) |  | 0 | 3 | 8 | 8 | 8 | 6 | 8 | 3 | 6 | 3 | 5 | 3 | 3 | 3
| EC Lay-down Area (acres) |  | 0 | 40 | 160 | 160 | 120 | 120 | 200 | 80 | 160 | 40 | 80 | 40 | 40 | 40
| Total Turbines |  | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2415.2277

## WC-UNC
Toggle
OUTPUT -WEST COAST UNCONSTRAINED DEMAND PIPELINE scenario
1. link procurement timelines in column A (one for each item)
[16 empty] | WC-Undeveloped | 1 | 2. copy/paste from cell C10 into new row
|  | Year | [15 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 |  |  | 166.7039
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 |  |  | 111.0665
ROTOR BLADES, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 100.035 | 200.0383 | 200.0383 | 0 | 0 | 0 | 0 | 0 |  |  | 500.1116
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.263 | 83.2891 | 66.6473 | 0 | 0 |  |  | 333.1994
NACELLES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 |  |  | 166.7039
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 |  |  | 111.0665
TOWERS, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 |  |  | 166.7039
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 |  |  | 111.0665
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | Transition Piece | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | Jackets (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | GBF (turbine) | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 |  |  | 277.7703
1 | Jacket (Substation) | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  |  | 9
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 |  |  | 9
CABLES
1 | Array cable, km | 0 | 0 | 0 | 0 | 0 | 122.0428 | 244.0467 | 244.0467 | 223.5809 | 101.6127 | 81.3097 | 0 | 0 |  |  | 1016.6394
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 205 | 105 | 105 | 0 | 0 |  |  | 955
| Total Turbines | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 0 | 0 | 277.7703
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 |  | 166.7039
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 |  | 111.0665
ROTOR BLADES, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 100.035 | 200.0383 | 200.0383 | 0 | 0 | 0 | 0 | 0 |  | 500.1116
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.263 | 83.2891 | 66.6473 | 0 | 0 |  | 333.1994
NACELLES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 |  | 166.7039
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 |  | 111.0665
TOWERS, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 |  | 166.7039
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 |  | 111.0665
FOUNDATIONS
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | Floating (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 |  | 277.7703
1 | Floating (floating OSS) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  | 9
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  | 9
CABLES
1 | Array cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 122.0428 | 244.0467 | 244.0467 | 223.5809 | 101.6127 | 81.3097 | 0 | 0 |  | 1016.6394
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 205 | 105 | 105 | 0 | 0 |  | 955
| Total Turbines | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 0 | 277.7703
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 0 | 0 | 0 | 0 | 0 | 500.1752 | 1500.3665 | 2500.5578 | 3600.1359 | 4099.8704 | 4499.7544 | 4499.7544 | 4499.7544 | 4499.7544
| Installed MW |  | 0 | 0 | 0 | 0 | 0 | 0 | 500.1752 | 1000.1913 | 1000.1913 | 1099.5781 | 499.7345 | 399.884 | 0 | 0 | 4499.7544
| Projects Constructed |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 9
| TURBINES (total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 277.7703
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 | 166.7039
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 111.0665
ROTOR BLADES
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100.035 | 200.0383 | 200.0383 | 0 | 0 | 0 | 0 | 0 | 500.1116
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.263 | 83.2891 | 66.6473 | 0 | 0 | 333.1994
NACELLES
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 | 166.7039
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 111.0665
TOWERS
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 | 166.7039
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 111.0665
| FOUNDATIONS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Floating (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 277.7703
| Floating (floating OSS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 9
SUBSTATIONS
| Floating OSS Topside |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 9
CABLES, KM
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 122.0428 | 244.0467 | 244.0467 | 223.5809 | 101.6127 | 81.3097 | 0 | 0 | 1016.6394
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 205 | 105 | 105 | 0 | 0 | 955
VESSEL.DAYS
| Offshore tug |  | 0 | 0 | 0 | 0 | 0 | 0 | 362.4551 | 724.795 | 724.795 | 664.0136 | 301.7798 | 241.482 | 0 | 0
| Anchor Handling Vessel |  | 0 | 0 | 0 | 0 | 0 | 0 | 160.6853 | 321.3196 | 321.3196 | 294.3737 | 133.7865 | 107.055 | 0 | 0
| HLV (Substation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 20 | 10 | 10 | 0 | 0
| CLV |  | 0 | 0 | 0 | 0 | 0 | 0 | 106.5107 | 205.5117 | 205.5117 | 203.1452 | 97.6532 | 86.5774 | 0 | 0
VESSELS
| Long haul tugs |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 2 | 1 | 0 | 0
| Anchor Handling Vessel |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0
| CTV |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 11 | 13 | 13 | 13 | 12 | 11 | 11
| SOV |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 5 | 7 | 8 | 9 | 9 | 9 | 9
| CLV |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (m) |  | 0 | 0 | 0 | 0 | 0 | 0 | 1190.8934 | 2381.4078 | 2381.4078 | 2181.7026 | 991.5368 | 793.4205 | 0 | 0
| WC Lay-down Area (acres) |  | 0 | 0 | 0 | 0 | 0 | 0 | 66.69 | 133.3588 | 133.3588 | 122.1753 | 55.5261 | 44.4316 | 0 | 0
| Total Turbines |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | 277.7703

## FIX-EX
Toggle
| OUTPUT - EAST COAST UNCONSTRAINED DEMAND PIPELINE scenario | [14 empty] | FIX-Expand | 1
[17 empty] | 1 | 1. link procurement timelines in column A (one for each item)
2. copy/paste from cell C10 into new row
|  | Year | [15 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 |  |  | 131.9038
ROTOR BLADES, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 270.7113 | 0 | 0 |  |  | 395.7113
NACELLES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 |  |  | 131.9038
TOWERS, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 |  |  | 131.9038
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 |  |  | 65.9519
1 | Transition Piece | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 |  |  | 65.9519
1 | Jackets (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 |  |  | 65.9519
1 | GBF (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | Jacket (Substation) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 |  |  | 4
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0 |  |  | 4
CABLES
1 | Array cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.5 | 0 | 198.1607 | 0 | 0 |  |  | 289.6607
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 450 | 0 | 0 |  |  | 600
| Total Turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | 0 | 0 | 131.9038
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 |  | 131.9038
ROTOR BLADES, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 270.7113 | 0 | 0 |  | 395.7113
NACELLES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 |  | 131.9038
TOWERS, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 |  | 131.9038
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 |  | 65.9519
1 | Transition Piece | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0
1 | Jackets (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 |  | 65.9519
1 | GBF (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | Jacket (Substation) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 |  | 4
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 |  | 4
CABLES
1 | Array cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.5 | 0 | 198.1607 | 0 | 0 |  | 289.6607
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 450 | 0 | 0 |  | 600
| Total Turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | 0 | 131.9038
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 2374.2678 | 2374.2678 | 2374.2678 | 2374.2678
| Installed MW |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 1624.2678 | 0 | 0 | 2374.2678
| Projects Constructed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2
| TURBINES (total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | 131.9038
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | 131.9038
ROTOR BLADES
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 270.7113 | 0 | 0 | 395.7113
NACELLES
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | 131.9038
TOWERS
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | 131.9038
| FOUNDATIONS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | 131.9038
| Monopiles (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 | 65.9519
| Transition Piece |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 | 65.9519
| GBF (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 | 65.9519
| Jacket (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Jacket (OSS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 4
SUBSTATIONS
| OSS Topside |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 4
CABLES, KM
| Static Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.5 | 0 | 198.1607 | 0 | 0 | 289.6607
| Static Export Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 450 | 0 | 0 | 600
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Mob/demob time to be added
| WTIV (15 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.5 | 0 | 135.3557 | 0 | 0 |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.25 | 0 | 67.6778 | 0 | 0
| WTIV total days |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.75 | 0 | 203.0335 | 0 | 0
| HLV (Substation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 30 | 0 | 0
| CLV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.375 | 0 | 264.0402 | 0 | 0
| Rock dumping |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.25 | 0 | 67.6778 | 0 | 0
VESSELS
| WTIV (12 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
| HLV/WTIV (foundation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
| Total WTIV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
| HLV (Substation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
| Feeder Barges |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0
| CTV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 5 | 4 | 4
| SOV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2
| CLV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0
| scour protection vessel |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0
| EC Lay-down Area (acres) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 0
| Total Turbines |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | 131.9038

## FLOAT-EX
Toggle
OUTPUT -WEST COAST UNCONSTRAINED DEMAND PIPELINE scenario
1. link procurement timelines in column A (one for each item)
[16 empty] | WC-Undeveloped | 1 | 2. copy/paste from cell C10 into new row
|  | Year | [15 empty] | 3. update the $A$10 reference to the current row
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 |  |  | 299.6667
ROTOR BLADES, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 500 | 375 |  |  | 899
NACELLES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 |  |  | 299.6667
TOWERS, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 |  |  | 299.6667
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | Transition Piece | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | Jackets (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
1 | GBF (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 |  |  | 299.6667
1 | Jacket (Substation) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 |  |  | 8
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 | 0 |  |  | 8
CABLES
1 | Array cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.28 | 610 | 457.5 |  |  | 1096.78
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 440 | 320 |  |  | 860
| Total Turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 | 0 | 0 | 299.6667
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 |  | 299.6667
ROTOR BLADES, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 500 | 375 |  | 899
NACELLES, MW
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 |  | 299.6667
TOWERS, m
1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 |  | 299.6667
FOUNDATIONS
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | Floating (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 |  | 299.6667
1 | Floating (floating OSS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 |  | 8
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 |  | 8
CABLES
1 | Array cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.28 | 610 | 457.5 |  | 1096.78
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 440 | 320 |  | 860
| Total Turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 | 0 | 299.6667
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 3144 | 5394 | 5394
| Installed MW |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 3000 | 2250 | 5394
| Projects Constructed |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 5
| TURBINES (total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 | 299.6667
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 | 299.6667
ROTOR BLADES
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 500 | 375 | 899
NACELLES
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 | 299.6667
TOWERS
| 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 | 299.6667
| FOUNDATIONS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Floating (turbine) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 | 299.6667
| Floating (floating OSS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 | 8
SUBSTATIONS
| Floating OSS Topside |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3 | 8
CABLES, KM
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.28 | 610 | 457.5 | 1096.78
| Dynamic Array Cable, km |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 440 | 320 | 860
VESSEL.DAYS
| Offshore tug |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.9588 | 1811.6409 | 1358.7307
| Anchor Handling Vessel |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.551 | 803.1453 | 602.359
| HLV (Substation) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 40 | 30
| CLV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.32 | 452.5 | 348.375
VESSELS
| Long haul tugs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 5
| Anchor Handling Vessel |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3
| CTV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 11 | 11
| SOV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 5 | 5
| CLV |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2
Port Requirements
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (m) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285.7143 | 5952.381 | 4464.2857
| WC Lay-down Area (acres) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 333.3333 | 250
| Total Turbines |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125 | 299.6667

## EC-MED
MED - Medium Constrained scenario
Year
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTALS
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
| TURBINES ORDERED, MW | 42.7692 | 143 | 191 | 225 | 225 | 124.9744 | 200 | 200 | 183.3333 | 183.3333 | 183.3333 | 183.3333 | 183.3333 | 0 | 0 | 2268.4103
1 | 12 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 |  |  | 1299
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 |  |  | 416.6667
ROTOR BLADES, m
1 | 12 | 128.3077 | 330 | 375 | 375 | 375 | 74.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 99 | 198 | 300 | 300 | 300 | 600 | 600 | 300 | 300 | 300 | 300 | 300 |  |  | 3897
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 250 |  |  | 1250
NACELLES, MW
1 | 12 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 |  |  | 1299
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 |  |  | 416.6667
TOWERS, m
1 | 12 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 |  |  | 1299
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 |  |  | 416.6667
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 178.6399 | 158.0138 | 85.4278 | 83.5084 | 61.1111 | 95.0683 | 91.6667 |  |  | 1325.833
1 | Transition Piece | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 178.6399 | 158.0138 | 85.4278 | 83.5084 | 61.1111 | 95.0683 | 91.6667 |  |  | 1325.833
1 | Jackets (turbine) | 0 | 12.3182 | 7.9076 | 10.1545 | 0 | 17.534 | 44.6382 | 0 | 0 | 71.271 | 61.1111 | 44.1325 | 91.6667 |  |  | 360.7339
1 | GBF (turbine) | 10 | 33.6791 | 50.3056 | 46.157 | 120.347 | 29.3362 | 0 | 28.4525 | 0 | 28.5539 | 61.1111 | 44.1325 | 0 |  |  | 452.075
1 | Jacket (Substation) | 2 | 4.2268 | 5.9307 | 6.462 | 5.8098 | 2.6656 | 6.5388 | 6.9783 | 2.1969 | 5.8043 | 6.1856 | 6.8679 | 7.1429 |  |  | 68.8095
SUBSTATIONS
2 | OSS Topsides | 4.2314 | 3.947 | 6.0449 | 5.1642 | 2.5591 | 6.5388 | 5.0751 | 1.9972 | 5.2766 | 5.6232 | 6.2435 | 6.4935 | 0 |  |  | 59.1946
CABLES
1 | Array cable, km | 125.5024 | 364.8547 | 477.3153 | 449.2859 | 431.368 | 321.4808 | 439.2 | 605.3594 | 170.5449 | 547.7588 | 366 | 366 | 366 |  |  | 5030.6702
1 | Export cable, km | 256 | 392.0033 | 332.5347 | 430.6382 | 543.2762 | 210.6996 | 902.6944 | 431.3263 | 125.8207 | 705.6658 | 843.4864 | 775.0409 | 909.0909 |  |  | 6858.2773
0
TRANSPORT
| TURBINES, MW | 0 | 42.7692 | 143 | 191 | 225 | 225 | 124.9744 | 200 | 200 | 183.3333 | 183.3333 | 183.3333 | 183.3333 | 183.3333 | 0 | 2268.4103
1 | 12 | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 |  | 1299
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 |  | 416.6667
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 330 | 375 | 375 | 375 | 74.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 99 | 198 | 300 | 300 | 300 | 600 | 600 | 300 | 300 | 300 | 300 | 300 |  | 3897
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 250 |  | 1250
NACELLES, MW
1 | 12 | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 |  | 1299
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 |  | 416.6667
TOWERS, m
1 | 12 | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 |  | 1299
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 |  | 416.6667
| FOUNDATIONS |  | 42.7692 | 143 | 176.5027 | 204.6909 | 225 | 118.1735 | 223.2781 | 186.4663 | 85.4278 | 183.3333 | 183.3333 | 183.3333 | 183.3333 | 0 | 2138.6419
1 | Monopiles (turbine) | 0 | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 178.6399 | 158.0138 | 85.4278 | 83.5084 | 61.1111 | 95.0683 | 91.6667 |  | 1325.833
1 | Transition Piece | 0 | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 178.6399 | 158.0138 | 85.4278 | 83.5084 | 61.1111 | 95.0683 | 91.6667
1 | Jackets (turbine) | 0 | 0 | 12.3182 | 7.9076 | 10.1545 | 0 | 17.534 | 44.6382 | 0 | 0 | 71.271 | 61.1111 | 44.1325 | 91.6667 |  | 360.7339
1 | GBF (turbine) | 0 | 10 | 33.6791 | 50.3056 | 46.157 | 120.347 | 29.3362 | 0 | 28.4525 | 0 | 28.5539 | 61.1111 | 44.1325 | 0 |  | 452.075
1 | Jacket (Substation) | 0 | 2 | 4.2268 | 5.9307 | 6.462 | 5.8098 | 2.6656 | 6.5388 | 6.9783 | 2.1969 | 5.8043 | 6.1856 | 6.8679 | 7.1429 |  | 68.8095
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 4.2314 | 3.947 | 6.0449 | 5.1642 | 2.5591 | 6.5388 | 5.0751 | 1.9972 | 5.2766 | 5.6232 | 6.2435 | 6.4935 |  | 61.1946
CABLES
1 | Array cable, km | 0 | 125.5024 | 364.8547 | 477.3153 | 449.2859 | 431.368 | 321.4808 | 439.2 | 605.3594 | 170.5449 | 547.7588 | 366 | 366 | 366 |  | 5030.6702
1 | Export cable, km | 0 | 256 | 392.0033 | 332.5347 | 430.6382 | 543.2762 | 210.6996 | 902.6944 | 431.3263 | 125.8207 | 705.6658 | 843.4864 | 775.0409 | 909.0909 |  | 6858.2773
VESSELS
0
0
NOTE: This table is the FOUNDATION, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 2328.2308 | 4818.2308 | 7818.2308 | 10818.2308 | 12617.9231 | 15617.9231 | 18617.9231 | 21617.9231 | 24617.9231 | 27617.9231 | 30617.9231 | 33617.9231 | 33617.9231
| Installed MW |  | 0 | 513.2308 | 1815 | 2490 | 3000 | 3000 | 1799.6923 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 33617.9231
| Number of Projects |  | 0 | 2 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 48
| TURBINES, MW | 0 | 0 | 42.7692 | 143 | 191 | 225 | 225 | 124.9744 | 200 | 200 | 183.3333 | 183.3333 | 183.3333 | 183.3333 | 183.3333 | 2268.4103
| 12 |  | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 | 1299
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 416.6667
ROTOR BLADES, UNITS
| 12 |  | 0 | 128.3077 | 330 | 375 | 375 | 375 | 74.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 99 | 198 | 300 | 300 | 300 | 600 | 600 | 300 | 300 | 300 | 300 | 300 | 3897
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 250 | 1250
NACELLES, MW
| 12 |  | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 | 1299
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 416.6667
TOWERS, UNITS
| 12 |  | 0 | 42.7692 | 110 | 125 | 125 | 125 | 24.9744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100 | 1299
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 416.6667
FOUNDATIONS
| Monopiles (turbine) |  | 0 | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 178.6399 | 158.0138 | 85.4278 | 83.5084 | 61.1111 | 95.0683 | 91.6667 | 1325.833
| Transition Piece |  | 0 | 32.7692 | 97.0028 | 118.2894 | 148.3794 | 104.653 | 71.3033 | 178.6399 | 158.0138 | 85.4278 | 83.5084 | 61.1111 | 95.0683 | 91.6667 | 1325.833
| GBF (turbine) |  | 0 | 0 | 12.3182 | 7.9076 | 10.1545 | 0 | 17.534 | 44.6382 | 0 | 0 | 71.271 | 61.1111 | 44.1325 | 91.6667 | 360.7339
| Jacket (turbine) |  | 0 | 10 | 33.6791 | 50.3056 | 46.157 | 120.347 | 29.3362 | 0 | 28.4525 | 0 | 28.5539 | 61.1111 | 44.1325 | 0 | 452.075
| Jacket (Substation) |  | 0 | 2 | 4.2268 | 5.9307 | 6.462 | 5.8098 | 2.6656 | 6.5388 | 6.9783 | 2.1969 | 5.8043 | 6.1856 | 6.8679 | 7.1429 | 68.8095
SUBSTATIONS
| OSS Topside |  | 0 | 2 | 4.2314 | 3.947 | 6.0449 | 5.1642 | 2.5591 | 6.5388 | 5.0751 | 1.9972 | 5.2766 | 5.6232 | 6.2435 | 6.4935 | 61.1946
CABLES, KM
| Array cable, km |  |  | 125.5024 | 364.8547 | 477.3153 | 449.2859 | 431.368 | 321.4808 | 439.2 | 605.3594 | 170.5449 | 547.7588 | 366 | 366 | 366 | 5030.6702
| Export cable, km |  |  | 256 | 392.0033 | 332.5347 | 430.6382 | 543.2762 | 210.6996 | 902.6944 | 431.3263 | 125.8207 | 705.6658 | 843.4864 | 775.0409 | 909.0909 | 6858.2773
VESSELS, (Vessel.Day)
| WTIV (12 MW) |  | 0 | 64.1538 | 165 | 187.5 | 187.5 | 187.5 | 37.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 49.5 | 99 | 150 | 150 | 150 | 300 | 300 | 150 | 150 | 150 | 150 | 150
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 125 | 125 | 125
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 196.0228 | 252.8925 | 291.8046 | 337.5 | 150.9592 | 267.9599 | 279.6995 | 128.1416 | 168.0935 | 183.3333 | 208.8012 | 137.5
| WTIV Total Days |  |  | 128.3077 | 410.5228 | 539.3925 | 629.3046 | 675 | 338.4208 | 567.9599 | 579.6995 | 403.1416 | 443.0935 | 458.3333 | 483.8012 | 412.5
| HLV (Substation) |  | 0 | 20 | 42.3141 | 39.47 | 60.4491 | 51.6422 | 25.5911 | 65.388 | 50.7514 | 19.9715 | 52.7663 | 56.2324 | 62.4353 | 64.9351
| CLV |  | 0 | 161.3756 | 341.2145 | 408.4625 | 449.981 | 473.661 | 283.0451 | 565.4736 | 489.1714 | 304.0914 | 543.3562 | 532.3716 | 515.2602 | 548.7727
| Rock damping |  | 0 | 49.1538 | 145.5041 | 177.4341 | 222.5691 | 156.9794 | 106.9549 | 267.9599 | 237.0207 | 128.1416 | 125.2626 | 91.6667 | 142.6024 | 137.5
VESSELS, (Vessels needed)
| WTIV (12 MW) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3
|  |  |  | 1 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 2
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| feeder Barges |  | 0 | 4 | 6 | 8 | 8 | 8 | 6 | 8 | 8 | 6 | 6 | 6 | 6 | 6
| CTV |  | 0 | 6 | 12 | 18 | 23 | 27 | 29 | 33 | 38 | 42 | 46 | 50 | 54 | 58 | 58
| SOV |  | 0 | 2 | 5 | 9 | 13 | 17 | 20 | 24 | 28 | 32 | 36 | 40 | 44 | 48 | 48
| CLV |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 0
| scour protection vessel |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1
Interim Calcs
# of turbines available to the US market
| 12 |  | 2: 82.5; 5: 110; 9: 125; 13: 125; 17: 125; 20: 125
| 15 |  |  |  | 33 | 66 | 100 | 100 | 100 | 200 | 200 | 100 | 100 | 100 | 100 | 100
| 18 |  | 32: 83.3333; 36: 83.3333; 40: 83.3333; 44: 83.3333; 48: 83.3333
|  |  |  | 990 | 1815 | 2490 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000

## EC-LOW
LOW - Low Constrained scenario
Year
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTALS
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
| TURBINES ORDERED, MW | 42.7692 | 154 | 254.6667 | 300 | 199.9744 | 266.6667 | 266.6667 | 266.6667 | 182.2222 | 177.9342 | 111.1111 | 111.1111 | 81.4387 | 0 | 0 | 2415.2277
1 | 12 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 |  |  | 463.661
ROTOR BLADES, m
1 | 12 | 128.3077 | 330 | 500 | 500 | 199.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 132 | 264 | 400 | 400 | 800 | 800 | 800 | 400 | 200.4693 | 0 | 0 | 0 |  |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146.6667 | 333.3333 | 333.3333 | 333.3333 | 244.3162 |  |  | 1390.9829
NACELLES, MW
1 | 12 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 |  |  | 463.661
TOWERS, m
1 | 12 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 |  |  | 463.661
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 84.91 | 81.0491 | 37.037 | 57.6171 | 40.7194 |  |  | 1488.1543
1 | Transition Piece | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 84.91 | 81.0491 | 37.037 | 57.6171 | 40.7194 |  |  | 1488.1543
1 | Jackets (turbine) | 0 | 13.2657 | 10.5435 | 13.5394 | 0 | 37.4136 | 59.5176 | 0 | 0 | 69.1721 | 37.037 | 26.747 | 40.7194 |  |  | 307.9553
1 | GBF (turbine) | 10 | 36.2698 | 67.0742 | 61.5427 | 106.9614 | 62.5967 | 0 | 37.9366 | 0 | 27.713 | 37.037 | 26.747 | 0 |  |  | 473.8784
1 | Jacket (Substation) | 2 | 4.552 | 7.9076 | 8.616 | 5.1636 | 5.6879 | 8.7184 | 9.3044 | 2.1836 | 5.6334 | 3.7488 | 4.1624 | 3.1729 |  |  | 70.8509
SUBSTATIONS
2 | OSS Topsides | 4.6161 | 5.2627 | 8.0599 | 4.8194 | 5.6879 | 8.7184 | 6.7668 | 1.9173 | 5.2808 | 3.7488 | 4.1624 | 3.1729 | 0 |  |  | 62.2133
CABLES
1 | Array cable, km | 125.5024 | 398.0233 | 636.4205 | 599.0478 | 402.5659 | 714.5238 | 585.6 | 807.1459 | 163.7231 | 548.1873 | 244 | 244 | 178.8395 |  |  | 5647.5795
1 | Export cable, km | 256 | 427.6399 | 443.3796 | 574.1842 | 507.002 | 468.3015 | 1203.5925 | 575.1017 | 120.7878 | 706.2178 | 562.3243 | 516.694 | 444.2113 |  |  | 6805.4366
0
TRANSPORT
| TURBINES, MW | 0 | 42.7692 | 154 | 254.6667 | 300 | 199.9744 | 266.6667 | 266.6667 | 266.6667 | 182.2222 | 177.9342 | 111.1111 | 111.1111 | 81.4387 | 0 | 2415.2277
1 | 12 | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 |  | 463.661
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 330 | 500 | 500 | 199.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 132 | 264 | 400 | 400 | 800 | 800 | 800 | 400 | 200.4693 | 0 | 0 | 0 |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146.6667 | 333.3333 | 333.3333 | 333.3333 | 244.3162 |  | 1390.9829
NACELLES, MW
1 | 12 | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 |  | 463.661
TOWERS, m
1 | 12 | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 |  | 463.661
| FOUNDATIONS |  | 42.7692 | 154 | 235.3369 | 272.9212 | 199.9744 | 252.1553 | 297.7042 | 248.6217 | 84.91 | 177.9342 | 111.1111 | 111.1111 | 81.4387 | 0 | 2269.9881
1 | Monopiles (turbine) | 0 | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 84.91 | 81.0491 | 37.037 | 57.6171 | 40.7194 |  | 1488.1543
1 | Transition Piece | 0 | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 84.91 | 81.0491 | 37.037 | 57.6171 | 40.7194
1 | Jackets (turbine) | 0 | 0 | 13.2657 | 10.5435 | 13.5394 | 0 | 37.4136 | 59.5176 | 0 | 0 | 69.1721 | 37.037 | 26.747 | 40.7194 |  | 307.9553
1 | GBF (turbine) | 0 | 10 | 36.2698 | 67.0742 | 61.5427 | 106.9614 | 62.5967 | 0 | 37.9366 | 0 | 27.713 | 37.037 | 26.747 | 0 |  | 473.8784
1 | Jacket (Substation) | 0 | 2 | 4.552 | 7.9076 | 8.616 | 5.1636 | 5.6879 | 8.7184 | 9.3044 | 2.1836 | 5.6334 | 3.7488 | 4.1624 | 3.1729 |  | 70.8509
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 4.6161 | 5.2627 | 8.0599 | 4.8194 | 5.6879 | 8.7184 | 6.7668 | 1.9173 | 5.2808 | 3.7488 | 4.1624 | 3.1729 |  | 64.2133
CABLES
1 | Array cable, km | 0 | 125.5024 | 398.0233 | 636.4205 | 599.0478 | 402.5659 | 714.5238 | 585.6 | 807.1459 | 163.7231 | 548.1873 | 244 | 244 | 178.8395 |  | 5647.5795
1 | Export cable, km | 0 | 256 | 427.6399 | 443.3796 | 574.1842 | 507.002 | 468.3015 | 1203.5925 | 575.1017 | 120.7878 | 706.2178 | 562.3243 | 516.694 | 444.2113 |  | 6805.4366
VESSELS
0
0
NOTE: This table is the FOUNDATION, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 2493.2308 | 5813.2308 | 9813.2308 | 12612.9231 | 16612.9231 | 20612.9231 | 24612.9231 | 27492.9231 | 30495.2697 | 32495.2697 | 34495.2697 | 35961.1671 | 35961.1671
| Installed MW |  | 0 | 513.2308 | 1980 | 3320 | 4000 | 2799.6923 | 4000 | 4000 | 4000 | 2880 | 3002.3467 | 2000 | 2000 | 1465.8973 | 35961.1671
| Number of Projects |  | 0 | 2 | 3 | 5 | 5 | 4 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 2 | 50
| TURBINES |  | 0 | 42.7692 | 154 | 254.6667 | 300 | 199.9744 | 266.6667 | 266.6667 | 266.6667 | 182.2222 | 177.9342 | 111.1111 | 111.1111 | 81.4387 | 2415.2277
| 12 |  | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 | 463.661
ROTOR BLADES
| 12 |  | 0 | 128.3077 | 330 | 500 | 500 | 199.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 132 | 264 | 400 | 400 | 800 | 800 | 800 | 400 | 200.4693 | 0 | 0 | 0 | 4196.4693
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146.6667 | 333.3333 | 333.3333 | 333.3333 | 244.3162 | 1390.9829
NACELLES
| 12 |  | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 | 463.661
TOWERS
| 12 |  | 0 | 42.7692 | 110 | 166.6667 | 166.6667 | 66.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 66.8231 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 81.4387 | 463.661
FOUNDATIONS
| Monopiles (turbine) |  | 0 | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 84.91 | 81.0491 | 37.037 | 57.6171 | 40.7194 | 1488.1543
| Transition Piece |  | 0 | 32.7692 | 104.4645 | 157.7192 | 197.8392 | 93.0129 | 152.1449 | 238.1866 | 210.6851 | 84.91 | 81.0491 | 37.037 | 57.6171 | 40.7194 | 1488.1543
| GBF (turbine) |  | 0 | 0 | 13.2657 | 10.5435 | 13.5394 | 0 | 37.4136 | 59.5176 | 0 | 0 | 69.1721 | 37.037 | 26.747 | 40.7194 | 307.9553
| Jacket (turbine) |  | 0 | 10 | 36.2698 | 67.0742 | 61.5427 | 106.9614 | 62.5967 | 0 | 37.9366 | 0 | 27.713 | 37.037 | 26.747 | 0 | 473.8784
| Jacket (Substation) |  | 0 | 2 | 4.552 | 7.9076 | 8.616 | 5.1636 | 5.6879 | 8.7184 | 9.3044 | 2.1836 | 5.6334 | 3.7488 | 4.1624 | 3.1729 | 70.8509
SUBSTATIONS
| OSS Topside |  | 0 | 2 | 4.6161 | 5.2627 | 8.0599 | 4.8194 | 5.6879 | 8.7184 | 6.7668 | 1.9173 | 5.2808 | 3.7488 | 4.1624 | 3.1729 | 64.2133
CABLES, KM
| Array cable, km |  |  | 125.5024 | 398.0233 | 636.4205 | 599.0478 | 402.5659 | 714.5238 | 585.6 | 807.1459 | 163.7231 | 548.1873 | 244 | 244 | 178.8395 | 5647.5795
| Export cable, km |  |  | 256 | 427.6399 | 443.3796 | 574.1842 | 507.002 | 468.3015 | 1203.5925 | 575.1017 | 120.7878 | 706.2178 | 562.3243 | 516.694 | 444.2113 | 6805.4366
VESSEL DAYS
| WTIV (12 MW) |  | 0 | 64.1538 | 165 | 250 | 250 | 99.9615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 66 | 132 | 200 | 200 | 400 | 400 | 400 | 200 | 100.2347 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.3333 | 166.6667 | 166.6667 | 166.6667 | 122.1581
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 211.1014 | 337.19 | 389.0728 | 299.9615 | 322.1125 | 357.2799 | 372.9326 | 127.365 | 163.1432 | 111.1111 | 126.5462 | 61.0791
| WTIV Total Days |  |  | 128.3077 | 442.1014 | 719.19 | 839.0728 | 599.9231 | 722.1125 | 757.2799 | 772.9326 | 400.6984 | 430.0445 | 277.7778 | 293.2129 | 183.2372
| HLV (Substation) |  | 0 | 20 | 46.1608 | 52.6267 | 80.5987 | 48.1941 | 56.8788 | 87.184 | 67.6685 | 19.1727 | 52.8076 | 37.4883 | 41.6236 | 31.7294
| CLV |  | 0 | 161.3756 | 366.4158 | 535.95 | 593.308 | 447.392 | 595.7063 | 747.2981 | 645.5619 | 295.1277 | 545.6013 | 361.5811 | 350.1735 | 269.7627
| Rock damping |  | 0 | 49.1538 | 156.6968 | 236.5788 | 296.7588 | 139.5194 | 228.2173 | 357.2799 | 316.0277 | 127.365 | 121.5737 | 55.5556 | 86.4257 | 61.0791
VESSELS, (Vessels needed)
| WTIV (12 MW) |  | 0 | 1 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 3 | 5 | 5 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 2
|  |  |  | 1 | 2 | 3 | 4 | 3 | 3 | 4 | 4 | 2 | 2 | 2 | 2 | 1
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| feeder Barges |  | 0 | 4 | 6 | 10 | 10 | 8 | 8 | 8 | 8 | 6 | 6 | 4 | 4 | 4
| CTV |  | 0 | 6 | 12 | 20 | 27 | 30 | 35 | 41 | 46 | 49 | 52 | 54 | 56 | 57 | 57
| SOV |  | 0 | 2 | 5 | 10 | 15 | 19 | 24 | 29 | 34 | 38 | 42 | 45 | 48 | 50 | 50
| CLV |  | 0 | 1 | 2 | 3 | 3 | 2 | 3 | 4 | 3 | 2 | 3 | 2 | 2 | 2 | 0
| scour protection vessel |  |  | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1
Interim Calcs
# of turbines available to the US market
| 12 |  |  | 110 | 110 | 166.6667 | 166.6667 | 166.6667
| 15 |  |  |  | 44 | 88 | 133.3333 | 133.3333 | 266.6667 | 266.6667 | 266.6667 | 133.3333 | 133.3333 | 133.3333 | 133.3333 | 133.3333 |  | IF(AND('OUTPUT-UNC'!E$86>0,'OUTPUT-UNC'!E$87=0,'OUTPUT-UNC'!E$88=0),(Assumptions!$C$9/$B134),IF(AND('OUTPUT-UNC'!E$86>0,'OUTPUT-UNC'!E$87>0,'OUTPUT-UNC'!E$88=0),(Assumptions!$C$9/$B134/2),IF(AND('OUTPUT-UNC'!E$86>0,'OUTPUT-UNC'!E$87=0,'OUTPUT-UNC'!E$88>0),Assumptions!$C$9/$B134/2,IF(AND('OUTPUT-UNC'!E$86>0,'OUTPUT-UNC'!E$87>0,'OUTPUT-UNC'!E$88>0),Assumptions!$C$9/$B134/3,0))))
| 18 | [10 empty] | 48.8889 | 111.1111 | 111.1111 | 111.1111 | 111.1111
|  |  |  | 1320 | 1980 | 3320 | 4000 | 4000 | 4000 | 4000 | 4000 | 2880 | 4000 | 4000 | 4000 | 4000
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe here is the # of projects per year.

## EC-HIGH
HIGH - Highly Constrained scenario
Year
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTALS
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
| TURBINES ORDERED, MW | 42.7692 | 121.6667 | 150 | 150 | 150 | 150 | 150 | 104.9744 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 0 | 0 | 1630.5214
1 | 12 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 277.7778
ROTOR BLADES, m
1 | 12 | 128.3077 | 165 | 250 | 250 | 250 | 250 | 250 | 114.9231 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  |  | 2400
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166.6667 | 166.6667 | 166.6667 | 166.6667 | 166.6667 |  |  | 833.3333
NACELLES, MW
1 | 12 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 277.7778
TOWERS, m
1 | 12 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  |  | 277.7778
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 56.9518 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  |  | 957.2396
1 | Transition Piece | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 56.9518 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  |  | 957.2396
1 | Jackets (turbine) | 0 | 10.4805 | 6.2102 | 6.7697 | 0 | 21.0452 | 33.4786 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 |  |  | 256.7717
1 | GBF (turbine) | 10 | 28.6547 | 39.507 | 30.7713 | 80.2314 | 35.2107 | 0 | 14.9339 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 |  |  | 328.5073
1 | Jacket (Substation) | 2 | 3.5962 | 4.6576 | 4.308 | 3.8732 | 3.1994 | 4.9041 | 3.6627 | 1.4646 | 3.8695 | 4.1237 | 4.5786 | 4.7619 |  |  | 48.9996
SUBSTATIONS
2 | OSS Topsides | 3.87 | 3.1703 | 4.0299 | 3.4428 | 2.8439 | 4.3592 | 2.4694 | 1.3314 | 3.5178 | 3.7488 | 4.1624 | 4.329 | 0 |  |  | 41.275
CABLES
1 | Array cable, km | 125.5024 | 333.6963 | 383.3858 | 299.5239 | 287.5787 | 357.2619 | 292.8 | 294.5462 | 113.6966 | 365.1725 | 244 | 244 | 244 |  |  | 3585.1643
1 | Export cable, km | 256 | 358.5264 | 267.0961 | 287.0921 | 362.1841 | 234.1507 | 601.7963 | 209.8679 | 83.8804 | 470.4439 | 562.3243 | 516.694 | 606.0606 |  |  | 4816.1168
0
TRANSPORT
| TURBINES, MW | 0 | 42.7692 | 121.6667 | 150 | 150 | 150 | 150 | 150 | 104.9744 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 0 | 1630.5214
1 | 12 | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 277.7778
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 165 | 250 | 250 | 250 | 250 | 250 | 114.9231 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 2400
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166.6667 | 166.6667 | 166.6667 | 166.6667 | 166.6667 |  | 833.3333
NACELLES, MW
1 | 12 | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 277.7778
TOWERS, m
1 | 12 | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 |  | 800
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 |  | 277.7778
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 56.9518 | 55.6723 | 40.7407 | 63.3789 | 61.1111 |  | 957.2396
1 | Transition Piece | 0 | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 56.9518 | 55.6723 | 40.7407 | 63.3789 | 61.1111
1 | Jackets (turbine) | 0 | 0 | 10.4805 | 6.2102 | 6.7697 | 0 | 21.0452 | 33.4786 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 |  | 256.7717
1 | GBF (turbine) | 0 | 10 | 28.6547 | 39.507 | 30.7713 | 80.2314 | 35.2107 | 0 | 14.9339 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 |  | 328.5073
1 | Jacket (Substation) | 0 | 2 | 3.5962 | 4.6576 | 4.308 | 3.8732 | 3.1994 | 4.9041 | 3.6627 | 1.4646 | 3.8695 | 4.1237 | 4.5786 | 4.7619 |  | 48.9996
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 3.87 | 3.1703 | 4.0299 | 3.4428 | 2.8439 | 4.3592 | 2.4694 | 1.3314 | 3.5178 | 3.7488 | 4.1624 | 4.329 |  | 43.275
CABLES
1 | Array cable, km | 0 | 125.5024 | 333.6963 | 383.3858 | 299.5239 | 287.5787 | 357.2619 | 292.8 | 294.5462 | 113.6966 | 365.1725 | 244 | 244 | 244 |  | 3585.1643
1 | Export cable, km | 0 | 256 | 358.5264 | 267.0961 | 287.0921 | 362.1841 | 234.1507 | 601.7963 | 209.8679 | 83.8804 | 470.4439 | 562.3243 | 516.694 | 606.0606 |  | 4816.1168
VESSELS
0
0
NOTE: This table is the FOUNDATION, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 2173.2308 | 4173.2308 | 6173.2308 | 8173.2308 | 10173.2308 | 12173.2308 | 13632.9231 | 15632.9231 | 17632.9231 | 19632.9231 | 21632.9231 | 23632.9231 | 23632.9231
| Installed MW |  | 0 | 513.2308 | 1660 | 2000 | 2000 | 2000 | 2000 | 2000 | 1459.6923 | 2000 | 2000 | 2000 | 2000 | 2000 | 23632.9231
| Number of Projects |  | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 37
| TURBINES, MW | 0 | 0 | 42.7692 | 121.6667 | 150 | 150 | 150 | 150 | 150 | 104.9744 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 1630.5214
| 12 |  | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 800
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 277.7778
ROTOR BLADES, UNITS
| 12 |  | 0 | 128.3077 | 165 | 250 | 250 | 250 | 250 | 250 | 114.9231 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 2400
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166.6667 | 166.6667 | 166.6667 | 166.6667 | 166.6667 | 833.3333
NACELLES, MW
| 12 |  | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 800
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 277.7778
TOWERS, UNITS
| 12 |  | 0 | 42.7692 | 55 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 38.3077 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 800
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 55.5556 | 277.7778
| FOUNDATIONS |  | 0 | 42.7692 | 121.6667 | 138.6146 | 136.4606 | 150 | 141.8373 | 167.4586 | 97.8709 | 56.9518 | 122.2222 | 122.2222 | 122.2222 | 122.2222 | 1542.5187
| Monopiles (turbine) |  | 0 | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 56.9518 | 55.6723 | 40.7407 | 63.3789 | 61.1111 | 957.2396
| Transition Piece |  | 0 | 32.7692 | 82.5315 | 92.8974 | 98.9196 | 69.7686 | 85.5815 | 133.9799 | 82.937 | 56.9518 | 55.6723 | 40.7407 | 63.3789 | 61.1111 | 957.2396
| GBF (turbine) |  | 0 | 0 | 10.4805 | 6.2102 | 6.7697 | 0 | 21.0452 | 33.4786 | 0 | 0 | 47.514 | 40.7407 | 29.4217 | 61.1111 | 256.7717
| Jacket (turbine) |  | 0 | 10 | 28.6547 | 39.507 | 30.7713 | 80.2314 | 35.2107 | 0 | 14.9339 | 0 | 19.0359 | 40.7407 | 29.4217 | 0 | 328.5073
| Jacket (Substation) |  | 0 | 2 | 3.5962 | 4.6576 | 4.308 | 3.8732 | 3.1994 | 4.9041 | 3.6627 | 1.4646 | 3.8695 | 4.1237 | 4.5786 | 4.7619 | 48.9996
SUBSTATIONS
| OSS Topside |  | 0 | 2 | 3.87 | 3.1703 | 4.0299 | 3.4428 | 2.8439 | 4.3592 | 2.4694 | 1.3314 | 3.5178 | 3.7488 | 4.1624 | 4.329 | 43.275
CABLES, KM
| Array cable, km |  |  | 125.5024 | 333.6963 | 383.3858 | 299.5239 | 287.5787 | 357.2619 | 292.8 | 294.5462 | 113.6966 | 365.1725 | 244 | 244 | 244 | 3585.1643
| Export cable, km |  |  | 256 | 358.5264 | 267.0961 | 287.0921 | 362.1841 | 234.1507 | 601.7963 | 209.8679 | 83.8804 | 470.4439 | 562.3243 | 516.694 | 606.0606 | 4816.1168
VESSELS, (Vessel.Day)
| WTIV (12 MW) |  | 0 | 64.1538 | 82.5 | 125 | 125 | 125 | 125 | 125 | 57.4615 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333
| HLV/WTIV (foundation) |  | 0 | 64.1538 | 166.7793 | 198.6067 | 194.5364 | 225 | 181.1883 | 200.9699 | 146.8064 | 85.4278 | 112.0623 | 122.2222 | 139.2008 | 91.6667
| WTIV Total Days |  |  | 128.3077 | 349.2793 | 423.6067 | 419.5364 | 450 | 406.1883 | 425.9699 | 304.2679 | 268.7611 | 295.3956 | 305.5556 | 322.5341 | 275
| HLV (Substation) |  | 0 | 20 | 38.7005 | 31.7028 | 40.2994 | 34.4281 | 28.4394 | 43.592 | 24.6938 | 13.3144 | 35.1775 | 37.4883 | 41.6236 | 43.29
| CLV |  | 0 | 161.3756 | 317.0557 | 322.6205 | 306.654 | 322.4407 | 307.8532 | 383.6491 | 240.1035 | 209.3943 | 368.9041 | 361.5811 | 350.1735 | 372.5152
| Rock damping |  | 0 | 49.1538 | 123.7972 | 139.3461 | 148.3794 | 104.653 | 128.3723 | 200.9699 | 124.4055 | 85.4278 | 83.5084 | 61.1111 | 95.0683 | 91.6667
VESSELS, (Vessels needed)
| WTIV (12 MW) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| feeder Barges |  | 0 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| CTV |  | 0 | 6 | 12 | 16 | 19 | 22 | 25 | 28 | 29 | 32 | 36 | 39 | 42 | 45 | 45
| SOV |  | 0 | 2 | 5 | 8 | 11 | 14 | 17 | 20 | 22 | 25 | 28 | 31 | 34 | 37 | 37
| CLV |  | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 0
scour protection vessel | bar: 2 to 37
Interim Calcs
# of turbines available to the US market
| 12 |  | 2: 55; 5: 55; 8: 83.3333; 11: 83.3333; 14: 83.3333; 17: 83.3333; 20: 83.3333; 22: 83.3333
| 15 |  |  |  | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667 | 66.6667
| 18 |  | 25: 55.5556; 28: 55.5556; 31: 55.5556; 34: 55.5556; 37: 55.5556
|  |  |  | 660 | 1660 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000

## Aggregated
Transposed Table | Project COD
PROJECTS | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | EC-UNDEVELOPED | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | WC-UNDEVELOPED | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | FIX-Extend | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | FLOAT-Expand | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Total Lease Area, Acres | 0 | 55200 | 508588.6667 | 310477.6667 | 186336.6667 | 224046.5 | 314249 | 0 | 159694 | 0 | 93761.5 | 0 | 0 | 0 | Total Lease Area, Acres | [14 empty] | Total Lease Area, Acres | [14 empty] | Total Lease Area, Acres | [14 empty] | Total Lease Area, Acres
Number of Projects | 0 | 2 | 6 | 5 | 5 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | Number of Projects | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 3 | 4 | 2 | 2 | 1 | 2 | 1 | Number of Projects | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | Number of Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | Number of Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2
Total Project Capacity, MW | 0 | 532 | 4304 | 3802 | 2821 | 2368.6 | 2737 | 0 | 1797 | 0 | 759 | 0 | 0 | 0 | Total Project Capacity, MW | 0 | 0 | 0 | 0 | 608 | 536 | 2888.9938 | 2294 | 2931.9377 | 1502.1379 | 2652.2678 | 1067 | 1441.4916 | 924 | Total Project Capacity, MW | 0 | 0 | 0 | 0 | 0 | 0 | 500.1752 | 1000.1913 | 1000.1913 | 1099.5781 | 499.7345 | 399.884 | 0 | 0 | Total Project Capacity, MW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 1624.2678 | 0 | 0 | Total Project Capacity, MW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 3000 | 2250
Total # of 12 MW turbines | 0 | 42.7692 | 261.7949 | 187.5128 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total # of 12 MW turbines | 0 | 0 | 0 | 0 | 50.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total # of 12 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total # of 12 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total # of 12 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total # of 15 MW turbines | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 157.9067 | 182.4667 | 0 | 119.8 | 0 | 0 | 0 | 0 | 0 | Total # of 15 MW turbines | 0 | 0 | 0 | 0 | 0 | 35.7333 | 192.5996 | 152.9333 | 195.4625 | 0 | 0 | 0 | 0 | 0 | Total # of 15 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 0 | 0 | 0 | 0 | 0 | Total # of 15 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total # of 15 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.1667 | 0 | 0 | 0 | Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 147.3482 | 59.2778 | 80.0829 | 51.3333 | Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6667 | 0 | 90.2371 | 0 | 0 | Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125
Average Rated Power, MW | 0 | 12 | 12.9333 | 13.2 | 14.2 | 15 | 15 | 0 | 15 | 0 | 18 | 0 | 0 | 0 | Average Rated Power, MW | 0 | 0 | 0 | 0 | 12 | 15 | 15 | 15 | 15 | 18 | 18 | 18 | 18 | 18 | Average Rated Power, MW | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 18 | 18 | 18 | 0 | 0 | Average Rated Power, MW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18 | 0 | 0 | Average Rated Power, MW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18
AverageMin Water Depth, m | 0 | 36 | 24.1667 | 34.82 | 26.6 | 32.5 | 39.3333 | 0 | 29.55 | 0 | 38 | 0 | 0 | 0 | AverageMin Water Depth, m | 0 | 0 | 0 | 0 | 27.4 | 50 | 26.9808 | 29.6154 | 34.5 | 26 | 25.5 | 38 | 38 | 31 | AverageMin Water Depth, m | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 722 | 722 | 722 | 900 | 900 | 0 | 0 | AverageMin Water Depth, m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | AverageMin Water Depth, m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 60
Average Max Water Depth, m | 0 | 44.5 | 37.3333 | 47.3 | 35.2 | 45 | 50 | 0 | 42.75 | 0 | 60 | 0 | 0 | 0 | Average Max Water Depth, m | 0 | 0 | 0 | 0 | 0 | 60 | 39.9808 | 38.9487 | 48.75 | 26 | 38.5 | 50 | 52.5 | 43 | Average Max Water Depth, m | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1050 | 1050 | 1050 | 0 | 0 | 0 | 0 | Average Max Water Depth, m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 34 | 0 | 0 | Average Max Water Depth, m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1050 | 200
substructure: total monopiles, # | 0 | 32.7692 | 229.4935 | 179.5064 | 110.0667 | 72.2 | 65.0467 | 0 | 107.35 | 0 | 12.65 | 0 | 0 | 0 | substructure: total monopiles, # | 0 | 0 | 0 | 0 | 50.6667 | 17.8667 | 148.9449 | 136.6 | 141.7292 | 38.8861 | 73.6741 | 19.7593 | 41.5273 | 25.6667 | substructure: total spar buoys, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | substructure: total monopiles, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 | substructure: total spar buoys, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
substructure: total GBF, # | 0 | 0 | 29.1429 | 12 | 11 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | substructure: total GBF, # | 0 | 0 | 0 | 0 | 0 | 0 | 11.6222 | 34.1333 | 0 | 0 | 73.6741 | 19.7593 | 19.2778 | 25.6667 | substructure: total semi-subs, # | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 61.0877 | 27.763 | 22.2158 | 0 | 0 | substructure: total GBF, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8333 | 0 | 45.1186 | 0 | 0 | substructure: total semi-subs, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 166.6667 | 125
substructure: total jacket, # | 0 | 10 | 79.6795 | 76.3397 | 50 | 85.7067 | 76.42 | 0 | 12.45 | 0 | 29.5167 | 0 | 0 | 0 | substructure: total jacket, # | 0 | 0 | 0 | 0 | 0 | 17.8667 | 11.6222 | 0 | 32.4 | 0 | 0 | 19.7593 | 19.2778 | 0 | substructure: total TLP, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | substructure: total jacket, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | substructure: total TLP, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
substructure: Total OSP jacket, # | 0 | 2 | 10 | 9 | 6 | 4 | 4 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | substructure: Total OSP jacket, # | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 5 | 1 | 5 | 2 | 3 | 2 | substructure: Total OSPsemi-sub, # | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | substructure: Total OSP jacket, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | substructure: Total OSPsemi-sub, # | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3
# of OSP | 0 | 2 | 10 | 6 | 6 | 4 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | # of OSP | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 5 | 1 | 5 | 2 | 3 | 2 | # of OSP, floating | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | # of OSP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | # of OSP, floating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3
Static array cable length per turbine, km | 0 | 2.6876 | 2.5085 | 2.4521 | 2.1146 | 2.1362 | 3.3956 | 0 | 4.4743 | 0 | 7.0974 | 0 | 0 | 0 | Static array cable length per turbine, km | 0 | 0 | 0 | 0 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | Dynamic array cable length per turbine, km | 0 | 0 | 0 | 0 | 0 | 0 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 0 | 0 | Static array cable length per turbine, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.196 | 0 | 2.196 | 0 | 0 | Dynamic array cable length per turbine, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.66 | 3.66 | 3.66
Total static array cable length, km | 0 | 125.5024 | 862.2539 | 725.5871 | 409.009 | 339.1801 | 582.028 | 0 | 525 | 0 | 299.274 | 0 | 0 | 0 | Total static array cable length, km | 0 | 0 | 0 | 0 | 111.264 | 78.4704 | 422.9487 | 335.8416 | 429.2357 | 85.394 | 323.5767 | 130.174 | 175.862 | 112.728 | Total dynamic array cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 122.0428 | 244.0467 | 244.0467 | 223.5809 | 101.6127 | 81.3097 | 0 | 0 | Total static array cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.5 | 0 | 198.1607 | 0 | 0 | Total dynamic array cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.28 | 610 | 457.5
Static export cable length, km | 0 | 256 | 552.6603 | 462.5 | 297.679 | 173 | 235.405 | 0 | 154.5 | 0 | 72.405 | 0 | 0 | 0 | Static export cable length, km | 0 | 0 | 0 | 0 | 158 | 133 | 323.2603 | 402.2603 | 352.405 | 63 | 290 | 150 | 222.405 | 140 | Dynamic export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 205 | 105 | 105 | 0 | 0 | Static export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 150 | 0 | 0 | Dynamic export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 220 | 210
# of static export cables | 0 | 2 | 10 | 6 | 6 | 4 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | # of static export cables | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 5 | 1 | 5 | 2 | 3 | 2 | # of dynamic export cables | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | # of static export cables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | # of dynamic export cables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3
Total static export cable length, km | 0 | 256 | 926.4136 | 505.5 | 340.679 | 393 | 335.405 | 0 | 197.5 | 0 | 72.405 | 0 | 0 | 0 | Total static export cable length, km | 0 | 0 | 0 | 0 | 158 | 133 | 323.2603 | 690.2603 | 482.405 | 63 | 730 | 300 | 372.405 | 280 | Total dynamic export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 205 | 105 | 105 | 0 | 0 | Total static export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 450 | 0 | 0 | Total dynamic export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 440 | 320
HVAC | 0 | 2 | 10 | 6 | 6 | 4 | 4 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HVDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | HVDC | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 5 | 2 | 0 | 5 | 2 | 2 | 2 | HVDC | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | HVDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | HVDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 3
ACCELERATED | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Total Lease Area, Acres | 0 | 55200 | 508588.6667 | 310477.6667 | 186336.6667 | 224046.5 | 314249 | 0 | 159694 | 0 | 93761.5 | 0 | 0 | 0
Number of Projects | 0 | 2 | 6 | 5 | 6 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Total Project Capacity, MW | 0 | 532 | 4304 | 3802 | 3429 | 2904.6 | 6126.169 | 6626.169 | 6626.169 | 6626.169 | 6626.169 | 6626.169 | 6626.169 | 6626.169
Total # of 12 MW turbines | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total # of 15 MW turbines | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0
Total # of 18 MW turbines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205
Average Rated Power, MW | 0 | 12.4388 | 12.9333 | 13.2 | 14.2 | 15 | 15 | 15 | 15 | 18 | 18 | 18 | 18 | 18
AverageMin Water Depth, m
Average Max Water Depth, m
substructure: total monopiles, # | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916
substructure: total GBF, # | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222
substructure: total jacket, # | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422
substructure: total semi-subs, # | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 66.6794 | 66.6794 | 66.6794 | 66.6794 | 66.6794
substructure: Total OSP jacket, # | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
substructure: Total OSP floating, # | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2
# of OSP, fixed | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
# of OSP, floating | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Static array cable length per turbine, km | 0 | 1.3438 | 1.2543 | 1.2261 | 2.1553 | 2.1661 | 2.7958 | 1.098 | 3.3352 | 1.098 | 4.6467 | 1.098 | 1.098 | 1.098
Total static array cable length, km | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767
Static export cable length, km | 0 | 256 | 552.6603 | 462.5 | 455.679 | 306 | 558.6653 | 558.6653 | 558.6653 | 558.6653 | 558.6653 | 558.6653 | 558.6653 | 558.6653
# of static export cables | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Total static export cable length, km | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653
Dynamic array cable length per turbine, km | 0 | 0 | 0 | 0 | 0 | 0 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66
Total dynamic array cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 122.0428 | 244.0467 | 244.0467 | 244.0467 | 244.0467 | 244.0467 | 244.0467 | 244.0467
Dynamic export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 210 | 210 | 210 | 210 | 210
# of dynamic export cables | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Total dynamic export cable length, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 210 | 210 | 210 | 210 | 210
HVAC | 0 | 2 | 10 | 6 | 6 | 4 | 7 | 0 | 5 | 1 | 1 | 0 | 1 | 0
HVDC | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 7 | 5 | 7 | 7 | 7 | 7 | 7
Note on J34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added 500 MW to account for the additional 500 MW capability on the West Coast in 2029. Then assume constant build-out of 5.6 GW/yr on the AC and 1.0 GW/yr on the WC through 2035.

## GBF-UNC
GBF-UNC - Unconstrained scenario, with 33% GBF Foundations.
Year
|  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTALS
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
| TURBINES ORDERED, MW | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 0 | 2415.2277
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 463.661
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3563 | 568.5446 | 177.8333 | 240.2486 | 154 |  |  | 1390.9829
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 463.661
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  |  | 463.661
FOUNDATIONS
1 | Monopiles (turbine) | 14.1138 | 111.6442 | 88.3892 | 73.172 | 63.9012 | 117.0365 | 56.342 | 96.9966 | 12.8324 | 62.5399 | 19.5617 | 26.4273 | 16.94 |  |  | 759.897
1 | Transition Piece | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  |  | 767.5727
1 | Jackets (turbine) | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  |  | 767.5727
1 | GBF (turbine) | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  |  | 767.5727
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  |  | 71
SUBSTATIONS
2 | OSS Topsides | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 0 |  |  | 63
CABLES
1 | Array cable, km | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 |  |  | 6073.3296
1 | Export cable, km | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 |  |  | 6559.2332
TRANSPORT
| TURBINES, MW | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 0 | 2415.2277
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 463.661
ROTOR BLADES, m
1 | 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 |  | 4196.4693
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3563 | 568.5446 | 177.8333 | 240.2486 | 154 |  | 1390.9829
NACELLES, MW
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 463.661
TOWERS, m
1 | 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 |  | 1398.8231
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 |  | 463.661
FOUNDATIONS
1 | Monopiles (turbine) | 0 | 14.1138 | 111.6442 | 88.3892 | 73.172 | 63.9012 | 117.0365 | 56.342 | 96.9966 | 12.8324 | 62.5399 | 19.5617 | 26.4273 | 16.94 |  | 759.897
1 | Transition Piece | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111
1 | Jackets (turbine) | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  | 767.5727
1 | GBF (turbine) | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 |  | 767.5727
1 | Jacket (Substation) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 |  | 71
SUBSTATIONS
1 | OSS Topsides | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 |  | 65
CABLES
1 | Array cable, km | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 |  | 6073.3296
1 | Export cable, km | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 |  | 6559.2332
VESSELS
0
0
NOTE: This table is the FOUNDATION, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW |  | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 20592.332 | 22886.332 | 27615.2697 | 29117.4076 | 32528.6754 | 33595.6754 | 35037.1671 | 35961.1671 | 35961.1671
| Installed MW |  | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 5625.9938 | 2294 | 4728.9377 | 1502.1379 | 3411.2678 | 1067 | 1441.4916 | 924 | 35961.1671
| Number of Projects |  | 0 | 2 | 6 | 5 | 6 | 3 | 7 | 3 | 6 | 2 | 3 | 1 | 2 | 1 | 47
| TURBINES, MW | 0 | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2415.2277
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 463.661
ROTOR BLADES, UNITS
| 12 |  | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 |  | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1125.1988 | 458.8 | 945.7875 | 0 | 0 | 0 | 0 | 0 | 4196.4693
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.3563 | 568.5446 | 177.8333 | 240.2486 | 154 | 1390.9829
NACELLES, MW
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 463.661
TOWERS, UNITS
| 12 |  | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 |  | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 375.0663 | 152.9333 | 315.2625 | 0 | 0 | 0 | 0 | 0 | 1398.8231
| 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.4521 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 463.661
| FOUNDATIONS |  | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 170.7333 | 293.9292 | 38.8861 | 189.5149 | 59.2778 | 80.0829 | 51.3333 | 2302.7181
33% | Monopiles (turbine) |  | 0 | 14.1138 | 111.6442 | 88.3892 | 73.172 | 63.9012 | 117.0365 | 56.342 | 96.9966 | 12.8324 | 62.5399 | 19.5617 | 26.4273 | 16.94 | 759.897
33.33% | Transition Piece |  | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 | 767.5727
33.33% | GBF (turbine) |  | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 | 767.5727
33.33% | Jacket (turbine) |  | 0 | 14.2564 | 112.772 | 89.2821 | 73.9111 | 64.5467 | 118.2187 | 56.9111 | 97.9764 | 12.962 | 63.1716 | 19.7593 | 26.6943 | 17.1111 | 767.5727
| Jacket (Substation) |  | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 5 | 11 | 1 | 6 | 2 | 3 | 2 | 71
SUBSTATIONS
| OSS Topside |  |  | 2 | 10 | 6 | 7 | 5 | 8 | 5 | 8 | 1 | 6 | 2 | 3 | 2 | 65
CABLES, KM
| Array cable, km |  |  | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 335.8416 | 954.2357 | 85.394 | 622.8507 | 130.174 | 175.862 | 112.728 | 6073.3296
| Export cable, km |  |  | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 690.2603 | 679.905 | 63 | 802.405 | 300 | 372.405 | 280 | 6559.2332
VESSELS, (Vessel.Day)
| WTIV (12 MW) |  | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 562.5994 | 229.4 | 472.8938 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125.1782 | 284.2723 | 88.9167 | 120.1243 | 77
| HLV/WTIV (foundation) |  | 0 | 42.5554 | 336.6243 | 266.5069 | 220.6247 | 192.6718 | 352.8827 | 169.8797 | 292.4595 | 38.6917 | 188.5673 | 58.9814 | 79.6825 | 51.0767
| WTIV Total Days |  |  | 106.7092 | 844.0981 | 701.2762 | 586.2247 | 483.1318 | 915.4821 | 399.2797 | 765.3533 | 163.8699 | 472.8396 | 147.8981 | 199.8068 | 128.0767
| HLV (Substation) |  | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 50 | 80 | 10 | 60 | 20 | 30 | 20
| CLV |  | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 837.9105 | 432.5255 | 766.5352 | 153.0985 | 588.3139 | 181.5435 | 251.0667 | 166.182
| Rock dumping |  | 0 | 21.1708 | 167.4664 | 132.5838 | 109.758 | 95.8518 | 175.5547 | 84.513 | 145.4949 | 19.2486 | 93.8099 | 29.3425 | 39.641 | 25.41
VESSELS, (Vessels needed)
| WTIV (12 MW) |  | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) |  | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1
| HLV/WTIV (foundation) |  | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| Total WTIV |  | 0 | 2 | 5 | 5 | 4 | 3 | 5 | 2 | 4 | 2 | 3 | 2 | 2 | 2
|  |  |  | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| HLV (Substation) |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| feeder Barges |  | 0 | 4 | 10 | 10 | 8 | 6 | 10 | 4 | 8 | 4 | 6 | 4 | 4 | 4
| CTV |  | 0 | 6 | 18 | 26 | 32 | 33 | 41 | 44 | 49 | 50 | 50 | 50 | 51 | 52 | 52
| SOV |  | 0 | 2 | 8 | 13 | 19 | 22 | 29 | 32 | 38 | 40 | 43 | 44 | 46 | 47 | 47
| CLV |  | 0 | 1 | 4 | 3 | 3 | 2 | 4 | 2 | 4 | 1 | 3 | 1 | 2 | 1 | 0
| scour protection vessel |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rouxel, Noe here is the # of projects per year.

## ACCEL
Toggle
| OUTPUT - ACCELERATED TOTAL DEMAND PIPELINE (EC AND WC) scenario | [13 empty] | EC-ACCEL | 1
1. link procurement timelines in column A (one for each item)
[15 empty] | WC-ACCEL | 1 |  | 2. copy/paste from cell C10 into new row
3. update the $A$10 reference to the current row
|  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | TOTAL |  | 4. select row and Ctrl-R to fill in to the right
Procurement timelines | DEMAND
PROCUREMENT & MANUFACTURING
TURBINES ORDERED, MW
1 | 12 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 509.9744
1 | 15 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 1847.4615
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 |  |  | 1840.6025
ROTOR BLADES, m
1 | 12 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1529.9231
1 | 15 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 1325.2338 | 1325.2338 | 0 | 0 | 0 | 0 | 0 |  |  | 5542.3845
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104.3615 | 1104.3615 | 1104.3615 | 1104.3615 | 1104.3615 |  |  | 5521.8075
NACELLES, MW
1 | 12 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 509.9744
1 | 15 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 1847.4615
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 |  |  | 1840.6025
TOWERS, m
1 | 12 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 509.9744
1 | 15 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 |  |  | 1847.4615
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 |  |  | 1840.6025
FOUNDATIONS
1 | Monopiles (turbine) | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 |  |  | 2371.7324
1 | Transition Piece | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 |  |  | 2371.7324
1 | Jackets (turbine) | 29.1429 | 12 | 11 | 0 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 |  |  | 473.1206
1 | GBF (turbine) | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 |  |  | 1013.9303
1 | Jacket (Substation) | 10 | 9 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 95
SUBSTATIONS
2 | OSS Topsides | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  | 15
CABLES
1 | Array cable, km | 10 | 6 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 92
1 | Export cable, km | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 15
| Total Turbines | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 0 | 0 | 4198.0384
TRANSPORT & STORE
TURBINES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 |  | 1847.4615
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 |  | 1840.6025
ROTOR BLADES, m
1 | 12 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1658.2308
1 | 15 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 1325.2338 | 1325.2338 | 0 | 0 | 0 | 0 | 0 |  | 5542.3845
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104.3615 | 1104.3615 | 1104.3615 | 1104.3615 | 1104.3615 |  | 5521.8075
NACELLES, MW
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 |  | 1847.4615
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 |  | 1840.6025
TOWERS, m
1 | 12 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 552.7436
1 | 15 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 |  | 1847.4615
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 |  | 1840.6025
FOUNDATIONS
1 | Monopiles (turbine) | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 |  | 2404.5016
1 | Transition Piece | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916
1 | Jackets (turbine) | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 |  | 473.1206
1 | GBF (turbine) | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 |  | 1023.9303
1 | Jacket (Substation) | 2 | 10 | 9 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 97
SUBSTATIONS
1 | OSS Topsides | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 15
CABLES
1 | Array cable, km | 2 | 10 | 6 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 94
1 | Export cable, km | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 15
| Total Turbines | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 0 | 4240.8076
NOTE: This table is the BASELINE, based on COD. All other activities are keyed off of COD.
COMMERCIAL OPERATION DATE (COD)
| Cumulative MW | 0 | 513.2308 | 4802.5844 | 8587.7382 | 12061.7382 | 14966.3382 | 21092.5073 | 27718.6763 | 34344.8454 | 40971.0144 | 47597.1835 | 54223.3525 | 60849.5216 | 67475.6906 | 67475.6906
| Installed MW | 0 | 513.2308 | 4289.3536 | 3785.1538 | 3474 | 2904.6 | 6126.169 | 6626.169 | 6626.169 | 6626.169 | 6626.169 | 6626.169 | 6626.169 | 6626.169 | 67475.6906
| Projects Constructed | 0 | 2 | 6 | 5 | 6 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 86
| TURBINES (total) |  | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 4240.8076
| 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 | 1847.4615
| 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 1840.6025
ROTOR BLADES
| 12 | 0 | 128.3077 | 785.3846 | 562.5385 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658.2308
| 15 | 0 | 0 | 229.563 | 307 | 549.2 | 580.92 | 1225.2338 | 1325.2338 | 1325.2338 | 0 | 0 | 0 | 0 | 0 | 5542.3845
| 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104.3615 | 1104.3615 | 1104.3615 | 1104.3615 | 1104.3615 | 5521.8075
NACELLES
| 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 | 1847.4615
| 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 1840.6025
TOWERS
| 12 | 0 | 42.7692 | 261.7949 | 187.5128 | 60.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.7436
| 15 | 0 | 0 | 76.521 | 102.3333 | 183.0667 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 0 | 0 | 0 | 0 | 0 | 1847.4615
| 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 1840.6025
| FOUNDATIONS | 0 | 42.7692 | 338.3159 | 267.8462 | 221.7333 | 193.64 | 354.656 | 354.656 | 354.656 | 354.656 | 354.656 | 354.656 | 354.656 | 354.656 | 3901.5526
| Monopiles (turbine) | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 2404.5016
| Transition Piece | 0 | 32.7692 | 229.4935 | 179.5064 | 160.7333 | 90.0667 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 213.9916 | 2404.5016 | 0.61629
| GBF (turbine) | 0 | 0 | 29.1429 | 12 | 11 | 0 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 52.6222 | 473.1206 | 0.12126
| Jacket (turbine) | 0 | 10 | 79.6795 | 76.3397 | 50 | 103.5733 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 88.0422 | 1023.9303 | 0.26244
| Jacket (OSS) | 0 | 2 | 10 | 9 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 97
| Floating (turbine) | 0 | 0 | 0 | 0 | 0 | 0 | 33.345 | 66.6794 | 66.6794 | 66.6794 | 66.6794 | 66.6794 | 66.6794 | 66.6794 | 500.1009
| Floating (floating OSS) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 15
SUBSTATIONS
| Fixed OSS Topside | 0 | 2 | 10 | 6 | 7 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 94
| Floating OSS Topside | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 15
CABLES, KM
| Static Array Cable, km | 0 | 125.5024 | 862.2539 | 725.5871 | 520.273 | 417.6505 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 1004.9767 | 10691.0804
| Static Export Cable, km | 0 | 256 | 926.4136 | 505.5 | 498.679 | 526 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 658.6653 | 7981.915
| Dynamic Array Cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 122.0428 | 244.0467 | 244.0467 | 244.0467 | 244.0467 | 244.0467 | 244.0467 | 244.0467 | 1830.3695
| Dynamic Export Cable, km | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 210 | 210 | 210 | 210 | 210 | 210 | 210 | 1590
VESSEL DAYS
| WTIV (12 MW) | 0 | 64.1538 | 392.6923 | 281.2692 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Mob/demob time to be added
| WTIV (15 MW) | 0 | 0 | 114.7815 | 153.5 | 274.6 | 290.46 | 612.6169 | 662.6169 | 662.6169 | 0 | 0 | 0 | 0 | 0 |  |  | NOTE: the Tufts study also has examples of staging + install time from 2 EU projects
| WTIV (18 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552.1808 | 552.1808 | 552.1808 | 552.1808 | 552.1808 |  |  |  | FYI -- from Tufts study. Table 5.
| HLV/WTIV (foundation) | 0 | 64.1538 | 463.7595 | 383.7692 | 316.1 | 290.46 | 453.0507 | 453.0507 | 453.0507 | 453.0507 | 453.0507 | 453.0507 | 453.0507 | 453.0507
| WTIV total days |  | 128.3077 | 971.2334 | 818.5385 | 681.7 | 580.92 | 1065.6676 | 1115.6676 | 1115.6676 | 1005.2314 | 1005.2314 | 1005.2314 | 1005.2314 | 1005.2314
| HLV (Substation) | 0 | 20 | 100 | 60 | 70 | 50 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
| CLV | 0 | 161.3756 | 783.1669 | 597.7718 | 548.738 | 441.9126 | 883.9105 | 907.9105 | 907.9105 | 907.9105 | 907.9105 | 907.9105 | 907.9105 | 907.9105
| Rock dumping | 0 | 49.1538 | 344.2403 | 269.2596 | 241.1 | 135.1 | 320.9873 | 320.9873 | 320.9873 | 320.9873 | 320.9873 | 320.9873 | 320.9873 | 320.9873
VESSELS
| WTIV (12 MW) | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WTIV (15 MW) | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| WTIV (18 MW) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3
| HLV/WTIV (foundation) | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Total WTIV | 0 | 2 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  | 1 | 4 | 4 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| HLV (Substation) | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Feeder Barges | 0 | 4 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| CTV | 0 | #REF! | 18 | 26 | 32 | 33 | 43 | 56 | 64 | 72 | 80 | 88 | 96 | 104 | 104
| SOV | 0 | 2 | 8 | 13 | 19 | 22 | 30 | 38 | 46 | 54 | 62 | 70 | 78 | 86 | 86
| CLV | 0 | 1 | 4 | 3 | 3 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Rock dumping vessel | 0 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Port Requirements
|  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
| Berth (Feeder barges) | 0 | 3 | 8 | 8 | 8 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| EC Lay-down Area (acres) | 0 | 29 | 116 | 116 | 87 | 87 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145
| WC Lay-down Area (acres) | 0 | 0 | 0 | 0 | 0 | 0 | 66.69 | 133.3588 | 133.3588 | 122.1753 | 55.5261 | 44.4316 | 0 | 0
| Total Turbines | 0 | 42.7692 | 338.3159 | 289.8462 | 243.7333 | 193.64 | 408.4113 | 441.7446 | 441.7446 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 368.1205 | 4240.8076